## COVER
TITLE |  | AOT028 DECEMBER SCHEDULE
2013-12-21 | V1.0 | WRITTEN

## CONTENTS
Summary DECEMBER 2013 | Nights of the month and the hours
Time Summary | The hours subdivision for each sub program
SCHEDULES | Night by night schedules
APPENDIX A | Summary of proposed object succession. Column B=Requested observation; Column K Planned Observation; Column L Difference(Negative for non planned)
APPENDIX B | Notes on Objects
APPENDIX C | Transits of KP objects

## Summary DECEMBER 2013
DATE | Fraction of night | Sunset | Sunrise | Evening Twilight | Morning Twilight | Sunset (UT) | Sunrise (UT) | Evening Twilight (UT) | Morning Twilight (UT) | Night Length (hr) | Hour Assigned (hr) | NIGHT BEGIN (UT) | NIGHT END (UT) | Special | Observer | Fract | Comment | END (UTt) Hr | HH | MM | BEG (UTt) Hr | HH | MM
2013-12-26 | 1 | 18:13 | 7:52 | 19:09 | 6:57 | 18:13 | 7:52 | 19:09 | 6:57 | 11.8 | 11.8 | 19:09 | 6:57 |  |  |  |  | 6.95 | 6 | 57 | 19.15 | 19 | 9
2013-12-27 | 1 | 18:14 | 7:52 | 19:09 | 6:57 | 18:14 | 7:52 | 19:09 | 6:57 | 11.8 | 11.8 | 19:09 | 6:57 |  |  |  |  | 6.95 | 6 | 57 | 19.15 | 19 | 9
2013-12-28 | 1 | 18:15 | 7:53 | 19:10 | 6:58 | 18:15 | 7:53 | 19:10 | 6:58 | 11.8 | 11.8 | 19:10 | 6:58 |  |  |  |  | 6.9667 | 6 | 58 | 19.1667 | 19 | 10
2013-12-29 | 1 | 18:15 | 7:53 | 19:10 | 6:58 | 18:15 | 7:53 | 19:10 | 6:58 | 11.8 | 11.8 | 19:10 | 6:58 |  |  |  |  | 6.9667 | 6 | 58 | 19.1667 | 19 | 10
2013-12-30 | 1 | 18:16 | 7:53 | 19:11 | 6:58 | 18:16 | 7:53 | 19:11 | 6:58 | 11.7833 | 11.7833 | 19:11 | 6:58 |  |  |  |  | 6.9667 | 6 | 58 | 19.1833 | 19 | 11
2013-12-31 | 1 | 18:17 | 7:53 | 19:12 | 6:58 | 18:17 | 7:53 | 19:12 | 6:58 | 11.7667 | 11.7667 | 19:12 | 6:58 |  |  |  |  | 6.9667 | 6 | 58 | 19.2 | 19 | 12

## TIME SUMMARY
NIGHT | TIME RML (hr) | TIME M (hr) | TIME KP (hr) | TIME MP (hr) | TIME OC (hr) | TIME AS (hr) | TIME IP (hr) | Planned Hours/d | BEDIN | TOT
2013-12-26 | 0 | 3 | 3 | 1.1667 | 3.1167 | 0 | 0 | 10.2833 | 1.4667 | 11.75
2013-12-27 | 0 | 2.6667 | 2.6667 | 1.5 | 3.1167 | 0 | 0 | 9.95 | 1.5 | 11.45
2013-12-28 | 0 | 2.6667 | 2.3333 | 1.75 | 3.1833 | 0 | 0 | 9.9333 | 1.3833 | 11.3167
2013-12-29 | 0 | 2.6667 | 2.3333 | 1.75 | 2.8333 | 0 | 0 | 9.5833 | 1.5 | 11.0833
2013-12-30 | 0 | 2.3333 | 3.1667 | 1.4167 | 3.1167 | 0 | 0 | 10.0333 | 1.4833 | 11.5167
2013-12-31 | 0 | 3 | 2.5 | 1.5 | 3.1167 | 0 | 0 | 10.1167 | 1.4889 | 11.6056
DECEMBER TOTAL (hr) | 0 | 16.3333 | 16 | 9.0833 | 18.4833 | 0 | 0 | 59.9 | 8.8222
% | 0 | 27.2677 | 26.7112 | 15.1642 | 30.857 | 0 | 0

## 2013-DECEMBER-26
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP |  |  |  | BEDIN
KP71 | 5 | 19:09 | 19:24 | 600 | 300 | 19:14 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 19.4 | 19 | 24
M24 | 2 | 19:24 | 19:44 | 900 | 300 | 19:31 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 19.7333 | 19 | 44
MP24 | 5 | 19:44 | 20:04 | 900 | 300 | 19:51 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.0667 | 20 | 4
MP21 | 4 | 20:04 | 20:24 | 900 | 300 | 20:11 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.4 | 20 | 24
M6 | 5 | 20:24 | 20:44 | 900 | 300 | 20:31 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 20.7333 | 20 | 44
M8 | 5 | 20:44 | 21:04 | 900 | 300 | 20:51 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 21.0667 | 21 | 4
M21 | 5 | 21:04 | 21:24 | 900 | 300 | 21:11 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 21.4 | 21 | 24
M34 | 5 | 21:24 | 21:44 | 900 | 300 | 21:31 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 21.7333 | 21 | 44
M9 | 3 | 21:44 | 22:04 | 900 | 300 | 21:51 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 22.0667 | 22 | 4
KP28 | 2 | 22:04 | 22:24 | 900 | 300 | 22:11 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 22.4 | 22 | 24
M14 | 3 | 22:24 | 22:44 | 900 | 300 | 22:31 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 22.7333 | 22 | 44
KP55 | 4 | 22:44 | 22:59 | 600 | 300 | 22:49 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 22.9833 | 22 | 59
KP11 | 3 | 22:59 | 23:19 | 900 | 300 | 23:06 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 23.3167 | 23 | 19
KP12 | 2 | 23:19 | 23:39 | 900 | 300 | 23:26 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 23.65 | 23 | 39
KP76 | 5 | 23:39 | 23:59 | 900 | 300 | 23:46 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 23.9833 | 23 | 59
OC101 | 5 | 23:59 | 0:15 | 900 | 60 | 0:06 |  | 0 | 0 | 0 | 0 | 960 | 0 | 0 | 24.25 | 24 | 15
OC102 | 5 | 0:15 | 0:36 | 1200 | 60 | 0:25 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 0.6 | 0 | 36
OC107 | 5 | 0:36 | 0:57 | 1200 | 60 | 0:46 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 0.95 | 0 | 57
OC116 | 5 | 0:57 | 1:18 | 1200 | 60 | 1:07 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 1.3 | 1 | 18
OC119 | 5 | 1:18 | 1:39 | 1200 | 60 | 1:28 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 1.65 | 1 | 39
OC120 | 5 | 1:39 | 2:00 | 1200 | 60 | 1:49 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 2 | 2 | 0
OC121 | 5 | 2:00 | 2:25 | 1200 | 300 | 2:10 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 2.4167 | 2 | 25
104TAU | NA | 2:25 | 2:27 | 60 | 60 | 2:25 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.45 | 2 | 27 | 120
S488 | NA | 2:27 | 2:31 | 180 | 60 | 2:28 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5167 | 2 | 31 | 240
S815 | NA | 2:31 | 2:52 | 1200 | 60 | 2:41 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8667 | 2 | 52 | 1260
YBP778 | NA | 2:52 | 3:08 | 900 | 60 | 2:59 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1333 | 3 | 8 | 960
YBP1194 | NA | 3:08 | 3:53 | 2400 | 300 | 3:28 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8833 | 3 | 53 | 2700
OC102 | 5 | 3:53 | 4:14 | 1200 | 60 | 4:03 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 4.2333 | 4 | 14
OC101 | 5 | 4:14 | 4:34 | 900 | 300 | 4:21 |  | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 4.5667 | 4 | 34
MP28 | 5 | 4:34 | 4:49 | 600 | 300 | 4:39 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 4.8167 | 4 | 49
MP30 | 4 | 4:49 | 5:04 | 600 | 300 | 4:54 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 5.0667 | 5 | 4
M97 | 5 | 5:04 | 5:24 | 900 | 300 | 5:11 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 5.4 | 5 | 24
KP57 | 4 | 5:24 | 5:39 | 600 | 300 | 5:29 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 5.65 | 5 | 39
KP7 | 4 | 5:39 | 5:59 | 900 | 300 | 5:46 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 5.9833 | 5 | 59
KP59 | 4 | 5:59 | 6:14 | 600 | 300 | 6:04 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 6.2333 | 6 | 14
KP63 | 4 | 6:14 | 6:34 | 900 | 300 | 6:21 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 6.5667 | 6 | 34
M85 | 5 | 6:34 | 6:54 | 900 | 300 | 6:41 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6.9 | 6 | 54
[7 empty] | TOTAL | 0 | 10800 | 10800 | 4200 | 11220 | 0 | 0 |  |  |  | 5280

## 2013-DECEMBER-27
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP |  |  |  | BEDIN
KP71 | 4 | 19:09 | 19:24 | 600 | 300 | 19:14 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 19.4 | 19 | 24
M17 | 3 | 19:24 | 19:44 | 900 | 300 | 19:31 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 19.7333 | 19 | 44
MP24 | 5 | 19:44 | 20:04 | 900 | 300 | 19:51 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.0667 | 20 | 4
MP22 | 4 | 20:04 | 20:24 | 900 | 300 | 20:11 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.4 | 20 | 24
M6 | 5 | 20:24 | 20:44 | 900 | 300 | 20:31 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 20.7333 | 20 | 44
KP29 | 2 | 20:44 | 21:04 | 900 | 300 | 20:51 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 21.0667 | 21 | 4
M21 | 5 | 21:04 | 21:24 | 900 | 300 | 21:11 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 21.4 | 21 | 24
MP23 | 4 | 21:24 | 21:44 | 900 | 300 | 21:31 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 21.7333 | 21 | 44
M18 | 3 | 21:44 | 22:04 | 900 | 300 | 21:51 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 22.0667 | 22 | 4
KP55 | 4 | 22:04 | 22:19 | 600 | 300 | 22:09 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 22.3167 | 22 | 19
M8 | 5 | 22:19 | 22:39 | 900 | 300 | 22:26 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 22.65 | 22 | 39
M34 | 5 | 22:39 | 22:59 | 900 | 300 | 22:46 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 22.9833 | 22 | 59
KP14 | 3 | 22:59 | 23:19 | 900 | 300 | 23:06 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 23.3167 | 23 | 19
KP76 | 5 | 23:19 | 23:39 | 900 | 300 | 23:26 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 23.65 | 23 | 39
OC101 | 5 | 23:39 | 23:55 | 900 | 60 | 23:46 |  | 0 | 0 | 0 | 0 | 960 | 0 | 0 | 23.9167 | 23 | 55
OC102 | 5 | 23:55 | 0:20 | 1200 | 300 | 0:05 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 24.3333 | 24 | 20
S364 | NA | 0:20 | 0:24 | 180 | 60 | 0:21 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 24 | 240
S978 | NA | 0:24 | 0:28 | 180 | 60 | 0:25 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46667 | 0 | 28 | 240
S1557 | NA | 0:28 | 0:33 | 240 | 60 | 0:30 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0 | 33 | 300
YBP401 | NA | 0:33 | 0:54 | 1200 | 60 | 0:43 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 54 | 1260
YBP1587 | NA | 0:54 | 1:29 | 1800 | 300 | 1:09 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4833 | 1 | 29 | 2100
OC107 | 5 | 1:29 | 1:50 | 1200 | 60 | 1:39 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 1.8333 | 1 | 50 | 1260
OC116 | 5 | 1:50 | 2:11 | 1200 | 60 | 2:00 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 2.1833 | 2 | 11
OC119 | 5 | 2:11 | 2:32 | 1200 | 60 | 2:21 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 2.5333 | 2 | 32
OC120 | 5 | 2:32 | 2:53 | 1200 | 60 | 2:42 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 2.8833 | 2 | 53
OC121 | 5 | 2:53 | 3:14 | 1200 | 60 | 3:03 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 3.2333 | 3 | 14
OC102 | 5 | 3:14 | 3:35 | 1200 | 60 | 3:24 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 3.5833 | 3 | 35
OC101 | 5 | 3:35 | 3:55 | 900 | 300 | 3:42 |  | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 3.9167 | 3 | 55
MP28 | 5 | 3:55 | 4:10 | 600 | 300 | 4:00 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 4.1667 | 4 | 10
MP30 | 5 | 4:10 | 4:25 | 600 | 300 | 4:15 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 4.4167 | 4 | 25
M97 | 5 | 4:25 | 4:45 | 900 | 300 | 4:32 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 4.75 | 4 | 45
KP57 | 4 | 4:45 | 5:00 | 600 | 300 | 4:50 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 5 | 5 | 0
KP7 | 4 | 5:00 | 5:20 | 900 | 300 | 5:07 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 5.3333 | 5 | 20
KP59 | 4 | 5:20 | 5:35 | 600 | 300 | 5:25 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 5.5833 | 5 | 35
KP63 | 4 | 5:35 | 5:55 | 900 | 300 | 5:42 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 5.9167 | 5 | 55
M85 | 5 | 5:55 | 6:15 | 900 | 300 | 6:02 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6.25 | 6 | 15
[7 empty] | TOTAL | 0 | 9600 | 9600 | 5400 | 11220 | 0 | 0 |  |  |  | 5400

## 2013-DECEMBER-28
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP |  |  |  | BEDIN
MP24 | 5 | 19:10 | 19:30 | 900 | 300 | 19:17 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 19.5 | 19 | 30
M17 | 3 | 19:30 | 19:50 | 900 | 300 | 19:37 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 19.8333 | 19 | 50
KP71 | 4 | 19:50 | 20:05 | 600 | 300 | 19:55 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 20.0833 | 20 | 5
MP22 | 4 | 20:05 | 20:25 | 900 | 300 | 20:12 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.4167 | 20 | 25
M6 | 5 | 20:25 | 20:45 | 900 | 300 | 20:32 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 20.75 | 20 | 45
KP30 | 2 | 20:45 | 21:05 | 900 | 300 | 20:52 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 21.0833 | 21 | 5
M21 | 5 | 21:05 | 21:25 | 900 | 300 | 21:12 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 21.4167 | 21 | 25
MP23 | 4 | 21:25 | 21:45 | 900 | 300 | 21:32 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 21.75 | 21 | 45
KP31 | 2 | 21:45 | 22:05 | 900 | 300 | 21:52 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 22.0833 | 22 | 5
KP55 | 4 | 22:05 | 22:20 | 600 | 300 | 22:10 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 22.3333 | 22 | 20
M8 | 5 | 22:20 | 22:40 | 900 | 300 | 22:27 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 22.6667 | 22 | 40
M34 | 5 | 22:40 | 23:00 | 900 | 300 | 22:47 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 23 | 23 | 0
MP25 | 4 | 23:00 | 23:15 | 600 | 300 | 23:05 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 23.25 | 23 | 15
KP76 | 5 | 23:15 | 23:35 | 900 | 300 | 23:22 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 23.5833 | 23 | 35
OC101 | 5 | 23:35 | 23:55 | 900 | 300 | 23:42 |  | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 23.9167 | 23 | 55
OC102 | 5 | 23:55 | 0:16 | 1200 | 60 | 0:05 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 24.2667 | 24 | 16
OC107 | 5 | 0:16 | 0:37 | 1200 | 60 | 0:26 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 0.61667 | 0 | 37
OC116 | 5 | 0:37 | 0:58 | 1200 | 60 | 0:47 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 0.96667 | 0 | 58
OC122 | 5 | 0:58 | 1:19 | 1200 | 60 | 1:08 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 1.3167 | 1 | 19
OC123 | 5 | 1:19 | 1:40 | 1200 | 60 | 1:29 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 1.6667 | 1 | 40
OC124 | 5 | 1:40 | 2:05 | 1200 | 300 | 1:50 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 2.0833 | 2 | 5
104Tau | NA | 2:05 | 2:07 | 60 | 60 | 2:05 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1167 | 2 | 7 | 120
YBP1514 | NA | 2:07 | 2:48 | 2400 | 60 | 2:27 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 2 | 48 | 2460
YBP1722 | NA | 2:48 | 3:19 | 1800 | 60 | 3:03 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3167 | 3 | 19 | 1860
S488 | NA | 3:19 | 3:23 | 180 | 60 | 3:20 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3833 | 3 | 23 | 240
S1557 | NA | 3:23 | 3:28 | 240 | 60 | 3:25 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4667 | 3 | 28 | 300
OC102 | 5 | 3:28 | 3:49 | 1200 | 60 | 3:38 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 3.8167 | 3 | 49
OC101 | 5 | 3:49 | 4:09 | 900 | 300 | 3:56 |  | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 4.15 | 4 | 9
MP29 | 4 | 4:09 | 4:24 | 600 | 300 | 4:14 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 4.4 | 4 | 24
MP30 | 5 | 4:24 | 4:39 | 600 | 300 | 4:29 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 4.65 | 4 | 39
M97 | 5 | 4:39 | 4:59 | 900 | 300 | 4:46 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 4.9833 | 4 | 59
KP57 | 4 | 4:59 | 5:14 | 600 | 300 | 5:04 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 5.2333 | 5 | 14
KP7 | 4 | 5:14 | 5:34 | 900 | 300 | 5:21 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 5.5667 | 5 | 34
KP59 | 4 | 5:34 | 5:49 | 600 | 300 | 5:39 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 5.8167 | 5 | 49
M105 | 5 | 5:49 | 6:09 | 900 | 300 | 5:56 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6.15 | 6 | 9
M85 | 5 | 6:09 | 6:29 | 900 | 300 | 6:16 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6.4833 | 6 | 29
[7 empty] | TOTAL | 0 | 9600 | 8400 | 6300 | 11460 | 0 | 0 |  |  |  | 4980

## 2013-DECEMBER-29
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP |  |  |  | BEDIN
KP71 | 4 | 19:10 | 19:25 | 600 | 300 | 19:15 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 19.4167 | 19 | 25
M17 | 3 | 19:25 | 19:45 | 900 | 300 | 19:32 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 19.75 | 19 | 45
MP24 | 5 | 19:45 | 20:05 | 900 | 300 | 19:52 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.0833 | 20 | 5
MP22 | 4 | 20:05 | 20:25 | 900 | 300 | 20:12 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.4167 | 20 | 25
M6 | 5 | 20:25 | 20:45 | 900 | 300 | 20:32 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 20.75 | 20 | 45
KP8 | 2 | 20:45 | 21:05 | 900 | 300 | 20:52 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 21.0833 | 21 | 5
M21 | 5 | 21:05 | 21:25 | 900 | 300 | 21:12 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 21.4167 | 21 | 25
MP23 | 4 | 21:25 | 21:45 | 900 | 300 | 21:32 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 21.75 | 21 | 45
KP13 | 2 | 21:45 | 22:05 | 900 | 300 | 21:52 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 22.0833 | 22 | 5
KP55 | 4 | 22:05 | 22:20 | 600 | 300 | 22:10 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 22.3333 | 22 | 20
M8 | 5 | 22:20 | 22:40 | 900 | 300 | 22:27 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 22.6667 | 22 | 40
M34 | 5 | 22:40 | 23:00 | 900 | 300 | 22:47 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 23 | 23 | 0
MP25 | 4 | 23:00 | 23:15 | 600 | 300 | 23:05 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 23.25 | 23 | 15
KP76 | 5 | 23:15 | 23:35 | 900 | 300 | 23:22 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 23.5833 | 23 | 35
OC101 | 5 | 23:35 | 23:55 | 900 | 300 | 23:42 |  | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 23.9167 | 23 | 55
OC102 | 5 | 23:55 | 0:16 | 1200 | 60 | 0:05 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 24.2667 | 24 | 16
OC116 | 5 | 0:16 | 0:37 | 1200 | 60 | 0:26 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 0.61667 | 0 | 37
OC119 | 5 | 0:37 | 0:58 | 1200 | 60 | 0:47 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 0.96667 | 0 | 58
OC120 | 5 | 0:58 | 1:19 | 1200 | 60 | 1:08 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 1.3167 | 1 | 19
OC121 | 5 | 1:19 | 1:44 | 1200 | 300 | 1:29 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1.7333 | 1 | 44
YBP1137 | NA | 1:44 | 2:45 | 3600 | 60 | 2:14 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.75 | 2 | 45 | 3660
YBP1075 | NA | 2:45 | 3:06 | 1200 | 60 | 2:55 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1 | 3 | 6 | 1260
S364 | NA | 3:06 | 3:14 | 180 | 300 | 3:07 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2333 | 3 | 14 | 480
OC102 | 5 | 3:14 | 3:35 | 1200 | 60 | 3:24 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 3.5833 | 3 | 35
OC101 | 5 | 3:35 | 3:55 | 900 | 300 | 3:42 |  | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 3.9167 | 3 | 55
MP29 | 4 | 3:55 | 4:10 | 600 | 300 | 4:00 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 4.1667 | 4 | 10
MP30 | 5 | 4:10 | 4:25 | 600 | 300 | 4:15 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 4.4167 | 4 | 25
M97 | 5 | 4:25 | 4:45 | 900 | 300 | 4:32 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 4.75 | 4 | 45
KP57 | 4 | 4:45 | 5:00 | 600 | 300 | 4:50 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 5 | 5 | 0
KP5 | 4 | 5:00 | 5:20 | 900 | 300 | 5:07 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 5.3333 | 5 | 20
KP59 | 4 | 5:20 | 5:35 | 600 | 300 | 5:25 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 5.5833 | 5 | 35
M105 | 5 | 5:35 | 5:55 | 900 | 300 | 5:42 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 5.9167 | 5 | 55
M85 | 5 | 5:55 | 6:15 | 900 | 300 | 6:02 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6.25 | 6 | 15
[7 empty] | TOTAL | 0 | 9600 | 8400 | 6300 | 10200 | 0 | 0 |  |  |  | 5400

## 2013-DECEMBER-30
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP |  |  |  | BEDIN
MP21 | 4 | 19:11 | 19:31 | 900 | 300 | 19:18 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 19.5167 | 19 | 31
KP55 | 4 | 19:31 | 19:46 | 600 | 300 | 19:36 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 19.7667 | 19 | 46
KP71 | 4 | 19:46 | 20:01 | 600 | 300 | 19:51 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 20.0167 | 20 | 1
M6 | 5 | 20:01 | 20:21 | 900 | 300 | 20:08 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 20.35 | 20 | 21
M34 | 5 | 20:21 | 20:41 | 900 | 300 | 20:28 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 20.6833 | 20 | 41
M21 | 5 | 20:41 | 21:01 | 900 | 300 | 20:48 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 21.0167 | 21 | 1
MP25 | 4 | 21:01 | 21:16 | 600 | 300 | 21:06 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 21.2667 | 21 | 16
MP28 | 5 | 21:16 | 21:31 | 600 | 300 | 21:21 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 21.5167 | 21 | 31
M8 | 5 | 21:31 | 21:51 | 900 | 300 | 21:38 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 21.85 | 21 | 51
KP18 | 2 | 21:51 | 22:11 | 900 | 300 | 21:58 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 22.1833 | 22 | 11
KP22 | 3 | 22:11 | 22:31 | 900 | 300 | 22:18 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 22.5167 | 22 | 31
KP78 | 3 | 22:31 | 22:51 | 900 | 300 | 22:38 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 22.85 | 22 | 51
MP11 | 3 | 22:51 | 23:11 | 900 | 300 | 22:58 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 23.1833 | 23 | 11
KP76 | 5 | 23:11 | 23:31 | 900 | 300 | 23:18 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 23.5167 | 23 | 31
OC101 | 5 | 23:31 | 23:47 | 900 | 60 | 23:38 |  | 0 | 0 | 0 | 0 | 960 | 0 | 0 | 23.7833 | 23 | 47
OC102 | 5 | 23:47 | 0:08 | 1200 | 60 | 23:57 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 24.1333 | 24 | 8
OC107 | 5 | 0:08 | 0:29 | 1200 | 60 | 0:18 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 0.48333 | 0 | 29
OC116 | 5 | 0:29 | 0:50 | 1200 | 60 | 0:39 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 0.83333 | 0 | 50
OC122 | 5 | 0:50 | 1:11 | 1200 | 60 | 1:00 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 1.1833 | 1 | 11
OC123 | 5 | 1:11 | 1:32 | 1200 | 60 | 1:21 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 1.5333 | 1 | 32
OC124 | 5 | 1:32 | 1:57 | 1200 | 300 | 1:42 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1.95 | 1 | 57
104TAU | NA | 1:57 | 1:59 | 60 | 60 | 1:57 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9833 | 1 | 59 | 120
S1607 | NA | 1:59 | 2:20 | 1200 | 60 | 2:09 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3333 | 2 | 20 | 1260
YBP401 | NA | 2:20 | 2:41 | 1200 | 60 | 2:30 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6833 | 2 | 41 | 1260
YBP1194 | NA | 2:41 | 3:26 | 2400 | 300 | 3:01 | M67 BEDIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4333 | 3 | 26 | 2700
OC101 | 5 | 3:26 | 3:42 | 900 | 60 | 3:33 |  | 0 | 0 | 0 | 0 | 960 | 0 | 0 | 3.7 | 3 | 42
OC102 | 5 | 3:42 | 4:07 | 1200 | 300 | 3:52 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 4.1167 | 4 | 7
MP29 | 4 | 4:07 | 4:22 | 600 | 300 | 4:12 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 4.3667 | 4 | 22
KP36 | 4 | 4:22 | 4:42 | 900 | 300 | 4:29 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 4.7 | 4 | 42
M97 | 5 | 4:42 | 5:02 | 900 | 300 | 4:49 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 5.0333 | 5 | 2
KP26 | 5 | 5:02 | 5:22 | 900 | 300 | 5:09 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 5.3667 | 5 | 22
KP5 | 4 | 5:22 | 5:42 | 900 | 300 | 5:29 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 5.7 | 5 | 42
M85 | 5 | 5:42 | 6:02 | 900 | 300 | 5:49 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6.0333 | 6 | 2
M105 | 5 | 6:02 | 6:22 | 900 | 300 | 6:09 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6.3667 | 6 | 22
KP65 | 3 | 6:22 | 6:42 | 900 | 300 | 6:29 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 6.7 | 6 | 42
[7 empty] | TOTAL | 0 | 8400 | 11400 | 5100 | 11220 | 0 | 0 |  |  |  | 5340

## 2013-DECEMBER-31
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP |  |  |  | BEDIN
MP21 | 4 | 19:12 | 19:32 | 900 | 300 | 19:19 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 19.5333 | 19 | 32
M24 | 2 | 19:32 | 19:52 | 900 | 300 | 19:39 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 19.8667 | 19 | 52
KP71 | 4 | 19:52 | 20:07 | 600 | 300 | 19:57 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 20.1167 | 20 | 7
M6 | 5 | 20:07 | 20:27 | 900 | 300 | 20:14 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 20.45 | 20 | 27
M34 | 5 | 20:27 | 20:47 | 900 | 300 | 20:34 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 20.7833 | 20 | 47
M21 | 5 | 20:47 | 21:07 | 900 | 300 | 20:54 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 21.1167 | 21 | 7
MP7 | 3 | 21:07 | 21:22 | 600 | 300 | 21:12 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 21.3667 | 21 | 22
MP28 | 5 | 21:22 | 21:37 | 600 | 300 | 21:27 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 21.6167 | 21 | 37
M8 | 5 | 21:37 | 21:57 | 900 | 300 | 21:44 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 21.95 | 21 | 57
M18 | 3 | 21:57 | 22:17 | 900 | 300 | 22:04 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 22.2833 | 22 | 17
KP76 | 5 | 22:17 | 22:37 | 900 | 300 | 22:24 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 22.6167 | 22 | 37
MP11 | 3 | 22:37 | 22:57 | 900 | 300 | 22:44 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 22.95 | 22 | 57
MP14 | 3 | 22:57 | 23:17 | 900 | 300 | 23:04 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 23.2833 | 23 | 17
KP55 | 4 | 23:17 | 23:32 | 600 | 300 | 23:22 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 23.5333 | 23 | 32
OC101 | 5 | 23:32 | 23:48 | 900 | 60 | 23:39 |  | 0 | 0 | 0 | 0 | 960 | 0 | 0 | 23.8 | 23 | 48
OC102 | 5 | 23:48 | 0:13 | 1200 | 300 | 23:58 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 24.2167 | 24 | 13
S978 | NA | 0:13 | 0:17 | 180 | 60 | 0:14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28333 | 0 | 17 | 240
YBP778 | NA | 0:17 | 0:33 | 900 | 60 | 0:24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0 | 33 | 960
YBP1514 | NA | 0:33 | 1:07 | 2000 | 60 | 0:49 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1222 | 1 | 7 | 2060
YBP1722 | NA | 1:07 | 1:42 | 1800 | 300 | 1:22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | 1 | 42 | 2100
OC107 | 5 | 1:42 | 2:03 | 1200 | 60 | 1:52 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 2.05 | 2 | 3
OC116 | 5 | 2:03 | 2:24 | 1200 | 60 | 2:13 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 2.4 | 2 | 24
OC122 | 5 | 2:24 | 2:45 | 1200 | 60 | 2:34 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 2.75 | 2 | 45
OC123 | 5 | 2:45 | 3:06 | 1200 | 60 | 2:55 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 3.1 | 3 | 6
OC124 | 5 | 3:06 | 3:27 | 1200 | 60 | 3:16 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 3.45 | 3 | 27
OC101 | 5 | 3:27 | 3:43 | 900 | 60 | 3:34 |  | 0 | 0 | 0 | 0 | 960 | 0 | 0 | 3.7167 | 3 | 43
OC102 | 5 | 3:43 | 4:08 | 1200 | 300 | 3:53 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 4.1333 | 4 | 8
KP63 | 4 | 4:08 | 4:28 | 900 | 300 | 4:15 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 4.4667 | 4 | 28
M85 | 5 | 4:28 | 4:48 | 900 | 300 | 4:35 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 4.8 | 4 | 48
M97 | 5 | 4:48 | 5:08 | 900 | 300 | 4:55 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 5.1333 | 5 | 8
KP26 | 5 | 5:08 | 5:28 | 900 | 300 | 5:15 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 5.4667 | 5 | 28
KP5 | 4 | 5:28 | 5:48 | 900 | 300 | 5:35 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 5.8 | 5 | 48
KP73 | 4 | 5:48 | 6:08 | 900 | 300 | 5:55 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 6.1333 | 6 | 8
M105 | 5 | 6:08 | 6:28 | 900 | 300 | 6:15 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6.4667 | 6 | 28
KP79 | 3 | 6:28 | 6:48 | 900 | 300 | 6:35 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 6.8 | 6 | 48
[7 empty] | TOTAL | 0 | 10800 | 9000 | 5400 | 11220 | 0 | 0 |  |  |  | 5360

## APPENDIX A
OBJECT | REQ. OBS | PRIORITY | 2013-12-26 | 2013-12-27 | 2013-12-28 | 2013-12-29 | 2013-12-30 | 2013-12-31 | PROG. OBS | DIFF
MP24 | 4 | 5 | 1 | 1 | 1 | 1 | 0 | 0 | 4 | 0
MP28 | 4 | 5 | 1 | 1 | 0 | 0 | 1 | 1 | 4 | 0
MP30 | 4 | 5 | 1 | 1 | 1 | 1 | 0 | 0 | 4 | 0
MP21 | 3 | 4 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 0
MP22 | 3 | 4 | 0 | 1 | 1 | 1 | 0 | 0 | 3 | 0
MP23 | 3 | 4 | 0 | 1 | 1 | 1 | 0 | 0 | 3 | 0
MP25 | 3 | 4 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 0
MP26 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
MP27 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
MP29 | 3 | 4 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 0
MP33 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
MP38 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
MP3 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP4 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP6 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP7 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | -1
MP8 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP9 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP11 | 2 | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0
MP12 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP13 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP14 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | -1
MP20 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M6 | 6 | 5 | [6 empty] | 6 | 0 | bar: 2013-12-26 to 2013-12-31
M8 | 6 | 5 | [6 empty] | 6 | 0 | bar: 2013-12-26 to 2013-12-31
M21 | 6 | 5 | [6 empty] | 6 | 0 | bar: 2013-12-26 to 2013-12-31
M34 | 6 | 5 | [6 empty] | 6 | 0 | bar: 2013-12-26 to 2013-12-31
M85 | 6 | 5 | [6 empty] | 6 | 0 | bar: 2013-12-26 to 2013-12-31
M97 | 6 | 5 | [6 empty] | 6 | 0 | bar: 2013-12-26 to 2013-12-31
M105 | 6 | 5 | 0 | 0 | 1 | 1 | 1 | 1 | 4 | -2
M9 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | -2
M14 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | -2
M17 | 3 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 3 | 0
M18 | 3 | 3 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | -1
M22 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
N23 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
M27 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
M33 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
M77 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
M82 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
M102 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
M104 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
KG7 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3
M2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M24 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0
M79 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M88 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M90 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M91 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M10 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M43 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M46 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M20 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
KG4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
KP76 | 6 | 5 | [6 empty] | 6 | 0 | bar: 2013-12-26 to 2013-12-31
KP5 | 3 | 4 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 0
KP7 | 3 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 0
KP55 | 5 | 4 | [6 empty] | 6 | 1 | bar: 2013-12-26 to 2013-12-31
KP57 | 4 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 4 | 0
KP59 | 4 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 4 | 0
KP71 | 5 | 4 | [6 empty] | 6 | 1 | bar: 2013-12-26 to 2013-12-31
KP63 | 3 | 4 | 1 | 1 | 0 | 0 | 0 | 1 | 3 | 0
KP64 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
KP65 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
KP26 | 2 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0
KP28 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
KP29 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
KP30 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
KP31 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
KP8 | 1 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
KP11 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
KP12 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
KP13 | 1 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
KP14 | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
KP18 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
KP22 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
KP36 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
KP37 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1
KP73 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
KP78 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
KP79 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | -1

## APPENDIX B
NOTE | COMMENT | AUTHOR
NOTE_01 | Assuming an air mass of 1.6 and a seeing of 1.0 arcsec, the HARPS-S ETC indicates that a total exposure of about 30 min is required for SPI study purposes. In order to conduct a pilot study for the detection of oscillations, we ask to perform fast time series observations during 1-2 nights at the beginning of the monitoring campaign, under the supervision of a trained visiting observer (Francesco Borsa) . A sequence of 30 spectra, each with an exposure time of 60 seconds is adequate for this purpose. In case of seeing worse than 1.5 arcsec, the exposure time could be increased up to 90 second per spectrum taking a sequence of 15-20 spectra. Owing to the CCD reading time (about 30 seconds per reading), the overhead increases to about 15-20 minutes for these short-cadence sequences. The total exposure time (Texp*n Spectra) for each epoch is determined by the requirement of reaching S/N >~ 400 per pixel at 395 nm (continuum between the H and K CaII lines). | AMa
NOTE_02 | Assuming an air mass of 1.6 and a seeing of 1.0 arcsec, the HARPS-S ETC indicates that about 30 min per exposure are required. It is mandatory to avoid saturation at longer wavelength , therefore the total exposure time needs to be splitted in subexposures of max 2-5 min. However, optimal subexposure times and saturation thresholds depend on the actual seeing. A sub-exposure time of 180-200 seconds appears to be adequate for an air mass around 1.6 and an average seeing of 1.0 arcsec. The total exposure time (Texp*n Spectra) for each epoch is determined by the requirement of reaching S/N >~ 400 per pixel at 395 nm (continuum between the H and K CaII lines). In order to study SPI effects at a single epoch, a coverage of at least three orbital periods is recommended (at least 10 observations). Continuous monitoring (dayly observations) would provide the best information, but -- taking into account possible difficulties in scheduling 10 consecutive nights -- a uniform phase coverage of the 3.3d period for three times along a maximum time span of 2-3 weeks is an acceptable compromise. A longer time baseline is not recommended because the pattern of stellar active regions may undergo rearrangement. | AMa
NOTE_03 | LP Spread 40 obs. along the semester, Observation starting sinceAugust 7 to January 31. Max Epochs 56 planned epochs 40 | SDe
NOTE_04 | LP Spread 40 obs. along the semester, Observation starting since September 2 to January 31. Max Epochs 48 planned epochs 40 | SDe
NOTE_05 | LP Spread 31 obs. along the semester, Observation starting since September 28 to January 31. | SDe
NOTE_06 | LP Spread 18 obs. along the semester, Observation starting since November 2 to January 31. | SDe
NOTE_07 | LP Spread 10 obs. along the semester, Observation starting since December 26 to January 31. HD106515A binary system with similar components separation= 6.9 arcsec pos angle= 267 deg (from N to E) delta V =0.27 DO brightest (=eastern) component only; due the high possibility of contamination with bad seeing this sar shall be observed with seeingbetter that 1.5 arcsc | SDe/RCl
NOTE_08 | LP Spread 56 obs. along the semester, Observation starting since August 26 to January 31. | SDe
NOTE_09 | LP Spread 11 obs. along the semester, Observation starting since December 4 to January 31. | SDe
NOTE_10 | TP Spread over semester (1/month) | SDe
NOTE_11 | red companion at 6.86 arcsec, Delta R=1.36 mag. DO brighter | RCl
NOTE_12 | binary system with similar components separation= 31 arcsec pos angle= (from N to E) delta V =0.05 DO northern component only SEE NOTE_36 | RCl
NOTE_13 | binary system with similar components separation= 11.2 arcsec, pos angle= (from N to E) delta I = 0.53, DO secondary only | RCl
NOTE_14 | Do not observe during AOT27 (Mail by SDe 2013-Feb-02) | SDe
NOTE_15 | The target is a OC Target once it will be observed with other oCs target it will be not observed in KP program | SDe
NOTE_16 | This star has been rejected. See the Aso's Mail of 2012-10-18. | RCl
NOTE_17 | This M star has been REJECTED. See Gmi's Mail of 2012 Dec 7th | RCl
NOTE_18 | M33 (ap_566) -- Star in double system | LAf
NOTE_19 | M43 (ap_3378) -- Double or multiple star | LAf
NOTE_20 | M44 (ap_846) -- High proper motion star (stella molto spostata nella finding chart, rispetto alle coordinate) | LAf
NOTE_21 | M54 (ap_2649) -- Star in double system | LAf
NOTE_22 | M61 (ap_3093) -- Star in double system con M64 | LAf
NOTE_23 | M64 (ap_3092) -- Star in double system con M61 | LAf
NOTE_24 | M69 (ap_2844) -- X-ray source | LAf
NOTE_25 | It is the brightest star in the field | ECo
NOTE_26 | G28-43 has been rejected. Mail sozzetti 2012-09-22 | RCl
NOTE_27 | Dopo una discussione con Silvano e Raffaele, si conviene che lo stato evolutivo di MP16 (G9-47) e' troppo avanzato perche' le variazioni RV di breve periodo osservate siano estrinseche. (Mail Sozzetti 2013-02-26) | Aso
NOTE_28 | Mail Aso: 2013-04-28. M67 va con ogni probabilita' stoppata, esibisce una variazione di 2.5 km/s in cinque giorni, e' quasi sicuramente una binaria. | Aso
NOTE_29 | Mail Gmi 2013-04-23: la stella M57 va tolta dal campione in quanto una binaria come hanno mostrato le ultime osservazioni . | Gmi
NOTE_30 | Mail ASo 2013-05-25: M83 andrebbe stoppata. Come da allegato, chiaramente binaria, probabilmente di relativamente corto periodo a vedere l'andamento, e con una massa minima non grande (nana bruna), a giudicare dall'escursione in RV. Pero' qui siamo abbastanza sicuramente al di fuori del range di masse 'planetario'. Mail del 2013-06-02: Abbiamo eliminato anche la 72 | Aso+Gmi
NOTE_31 | MAIL di Laura Affer del 2013-07-26: Confermo l'eliminazione dal catalogo di M58 e M94 in quanto classificate come G/K da Lepine (mai osservate), M50 in quanto binaria, M45 early e gigante. Mail di Alessandro Sozzetti 2013-0725: Tra gli oggetti che ti hanno fornito Laura e Giusi, M50 ha un excursus di oltre 40 km/s tra le due osservazioni prese a distanza di un mese e mezzo. Va stoppata, piuttosto che messa a priorita' media. | Laf+Aso
NOTE_32 | Vedi Mail di S. desidera del 2013-07-26 | SDe
NOTE_33 | Vedi Mail di S. desidera del 2013-07-26 | SDe
NOTE_34 | Mail Laf 2013-07-29: sono tutte stelle rigettate: ID RA DEC Mv N. Obs Note M5 02 56 34.4 +55 26 33 10,48 1 Mis-Id in a multiple system M19 22 10 44.7 +07 54 33 10,92 1 Sub-arcsec Binary M26 02 01 49.0 +16 28 03 10,65 2 Sub-arcsec Binary | Laf
NOTE_35 | M STARS refused see E-Mail by Gmi and Laf of 2013-08-29: --- Qui invece c'e' la lista delle stelle definitivamente rigettate: 02 34 09.9 +68 43 21 9,9 M3 Fast Rotator 23 31 19.7 +59 44 52 9,9 M4 Early 02 56 34.4 +55 26 33 10,48 M5 Mis-Id in a multiple system 00 11 21.9 +58 37 03 11,21 M13 Early 22 10 44.7 +07 54 33 10,92 M19 Sub-arcsec Binary 02 01 49.0 +16 28 03 10,65 M26 Sub-arcsec Binary 03:16:13.8 +58:10:03 10.53 M32 Double or multiple system 03:27:53.2 +51:19:55 10.89 M35 Early 04:41:29.7 +13:13:16 11.26 M38 Binary 03:38:48.2 +54:59:21 11.27 M39 Early 04:58:30.4 +51:48:17 11.52 M42 Early 20:31:32.8 +55:57:48 10.12 M45 Early -- gigante 22:12:56.7 +55:04:50 11.02 M50 Binary 06:40:56.7 +63:53:25 11.27 M57 Binary 21:48:46.5 +40:19:43 11.27 M58 Early 11:15:12.0 +54:09:27 11.70 M66 Binary 05:46:48.7 +66:30:12 11.77 M67 Binary 20:43:34.5 +24:07:41 11.95 M72 Fast Rotator 13:19:33.3 +35:06:43 9.51 M83 Binary 14:25:46.7 +23:37:14 9.99 M94 Early | GMi+LAf
NOTE_36 | KP76 is the south component of a binary. The North component is KP22 | SDe
NOTE_37 | MAIL Aso 2013 -10- 07. Se Giusi non lo ha ancora comunicato, suggerisco senz'altro di stoppare M51. Se ci sono due spettri non c'e' modo di beccare le RV giuste. | Aso
NOTE_38 | Mail di Gmi del 2013-11-14: M49 è una binaria | Gmi
NOTE_39 | Mail Sde (2013-12-17) Target in stand By for all the LP | SDe

## APPENDIX C
# | name | ut_ingress | ut_egress
| KP14=WASP-50 | 2013-12-26T22:12:27 | 2013-12-27T00:00:47
| KP18=WASP-12 | 2013-12-27T01:19:46 | 2013-12-27T04:15:26
| KP21=HAT-P-20 | 2013-12-27T04:20:40 | 2013-12-27T06:11:33
| KP22=XO-2 | 2013-12-27T04:30:16 | 2013-12-27T07:01:28
| KP23=HAT-P-30 | 2013-12-27T05:31:06 | 2013-12-27T07:38:50
| KP26=WASP-31 | 2013-12-27T06:25:26 | 2013-12-27T09:04:51
#
| KP11=HAT-P-16 | 2013-12-27T17:45:32 | 2013-12-27T20:49:17
| KP15=WASP-11 | 2013-12-27T20:42:46 | 2013-12-27T23:16:08
| KP8=WASP-32 | 2013-12-27T22:08:42 | 2013-12-28T00:34:09
| KP18=WASP-12 | 2013-12-28T03:31:24 | 2013-12-28T06:27:05
#
| KP14=WASP-50 | 2013-12-28T21:07:60 | 2013-12-28T22:56:21
| KP20=XO-4 | 2013-12-29T03:08:06 | 2013-12-29T07:32:06
| KP37=WASP-14 | 2013-12-29T03:49:32 | 2013-12-29T06:53:08
| KP18=WASP-12 | 2013-12-29T05:43:03 | 2013-12-29T08:38:44
#
| KP9=WASP-26 | 2013-12-29T18:13:35 | 2013-12-29T20:34:42
| KP22=XO-2 | 2013-12-29T19:17:02 | 2013-12-29T21:48:14
| KP19=HAT-P-24 | 2013-12-29T19:00:42 | 2013-12-29T22:42:19
| KP23=HAT-P-30 | 2013-12-30T00:58:10 | 2013-12-30T03:05:54
| KP21=HAT-P-20 | 2013-12-30T01:21:02 | 2013-12-30T03:11:55
#
| KP14=WASP-50 | 2013-12-30T20:03:33 | 2013-12-30T21:51:54
| KP16=XO-3 | 2013-12-31T20:12:18 | 2013-12-31T23:05:18
| KP27=HAT-P-21 | 2013-12-31T23:59:31 | 2014-01-01T03:39:51