## COVER
TITLE |  | AOT029 MARCH SCHEDULE
2014-02-20 | V1.0 | WRITTEN
2014-02-28 | V1.1 | INSERTED SCHEDULE AND Fixed problem in the calculation of the beginning and end of nights
2014-03-02 | V1.2 | Inserted new schedule
2014-MAR-03 | V1.3 | MODIFIED THE OC SCHEDULE FOR MARCH 4TH
2014-03-04 | V1.4 | Inserted new schedule and the last version of AppendixC
2014-MAR-10 | V1.5 | Inserted schedule of March 11st

## CONTENTS
Summary FEBRUARY 2014 | Nights of the month and the hours
Time Summary | The hours subdivision for each sub program
SCHEDULES | Night by night schedules
APPENDIX A | Summary of proposed object succession. Column B=Requested observation; Column K Planned Observation; Column L Difference(Negative for non planned)
APPENDIX B | Notes on Objects
APPENDIX C | Transits of KP objects

## Summary MARCH 2014
DATE | Fraction of night | Sunset | Sunrise | Evening Twilight | Morning Twilight | Sunset (UT) | Sunrise (UT) | Evening Twilight (UT) | Morning Twilight (UT) | Night Length (hr) | Hour Assigned (hr) | NIGHT BEGIN (UT) | NIGHT END (UT) | Special | Observer | Fract | Comment
2014-03-02 | 0.75 | 19:03 | 7:25 | 19:53 | 6:34 | 19:03 | 7:25 | 19:53 | 6:34 | 10.6833 | 8.0125 | 19:53 | 3:54 |  |  | BEGIN
2014-03-03 | 0.75 | 19:03 | 7:24 | 19:54 | 6:33 | 19:03 | 7:24 | 19:54 | 6:33 | 10.65 | 7.9875 | 19:54 | 3:53 |  |  | BEGIN
2014-03-04 | 0.75 | 19:04 | 7:23 | 19:55 | 6:32 | 19:04 | 7:23 | 19:55 | 6:32 | 10.6167 | 7.9625 | 19:55 | 3:53 |  |  | BEGIN
2014-03-05 | 0.75 | 19:04 | 7:21 | 19:55 | 6:31 | 19:04 | 7:21 | 19:55 | 6:31 | 10.6 | 7.95 | 19:55 | 3:52 |  |  | BEGIN
2014-03-06 | 0.75 | 19:05 | 7:20 | 19:56 | 6:30 | 19:05 | 7:20 | 19:56 | 6:30 | 10.5667 | 7.925 | 19:56 | 3:52 |  |  | BEGIN
2014-03-07 | 1 | 19:06 | 7:19 | 19:56 | 6:29 | 19:06 | 7:19 | 19:56 | 6:29 | 10.55 | 10.55 | 19:56 | 6:29 | RML |  | BEGIN
2014-03-08 | 0.75 | 19:06 | 7:18 | 19:57 | 6:28 | 19:06 | 7:18 | 19:57 | 6:28 | 10.5167 | 7.8875 | 19:57 | 3:50 |  |  | BEGIN
2014-03-09 | 0.75 | 19:07 | 7:17 | 19:58 | 6:26 | 19:07 | 7:17 | 19:58 | 6:26 | 10.4667 | 7.85 | 19:58 | 3:49 |  |  | BEGIN
2014-03-10 | 0.75 | 19:07 | 7:16 | 19:58 | 6:25 | 19:07 | 7:16 | 19:58 | 6:25 | 10.45 | 7.8375 | 19:58 | 3:48 |  |  | BEGIN
2014-03-11 | 1 | 19:08 | 7:15 | 19:59 | 6:24 | 19:08 | 7:15 | 19:59 | 6:24 | 10.4167 | 10.4167 | 19:59 | 6:24 | RML
2014-03-30 | 1 | 20:18 | 7:53 | 21:10 | 7:02 | 19:18 | 6:53 | 20:10 | 6:02 | 9.8667 | 9.8667 | 20:10 | 6:02 |  |  |  | Begin Saving Time(LT=UT+2hr)
2014-03-31 | 1 | 20:19 | 7:52 | 21:10 | 7:01 | 19:19 | 6:52 | 20:10 | 6:01 | 9.85 | 9.85 | 20:10 | 6:01 | RML

## TIME SUMMARY
NIGHT | TIME RML (hr) | TIME M (hr) | TIME KP (hr) | TIME MP (hr) | TIME OC (hr) | TIME AS (hr) | TIME IP (hr) | Planned Hours/d | TOT
2014-03-02 | 0 | 1.6667 | 1.3333 | 0.66667 | 3.9167 | 0 | 0 | 7.5833 | 7.5833
2014-03-03 | 0 | 1.6667 | 1.6667 | 0.66667 | 3.5667 | 0 | 0 | 7.5667 | 7.5667
2014-03-04 | 0 | 1.3333 | 1.6667 | 1 | 3.5667 | 0 | 0 | 7.5667 | 7.5667
2014-03-05 | 0 | 1.3333 | 1.5833 | 0.58333 | 3.9167 | 0 | 0 | 7.4167 | 7.4167
2014-03-06 | 0 | 1.3333 | 1.9167 | 0.66667 | 3.5667 | 0 | 0 | 7.4833 | 7.4833
2014-03-07 | 6.4833 | 0.86667 | 1.7167 | 0.26667 | 1.1167 | 0 | 0 | 10.45 | 10.45
2014-03-08 | 0 | 1.6667 | 1 | 0.91667 | 3.9167 | 0 | 0 | 7.5 | 7.5
2014-03-09 | 0 | 2.0167 | 2.25 | 0.91667 | 2.5 | 0 | 0 | 7.6833 | 7.6833
2014-03-10 | 0 | 3 | 3 | 1.8333 | 0 | 0 | 0 | 7.8333 | 7.8333
2014-03-11 | 4.2833 | 3 | 2.6667 | 1.3333 | 0 | 0 | 0 | 11.2833 | 11.2833
DECEMBER TOTAL (hr) | 10.7667 | 17.8833 | 18.8 | 8.85 | 26.0667 | 0 | 0 | 82.3667
% | 13.0716 | 21.7119 | 22.8248 | 10.7446 | 31.6471 | 0 | 0

## 2014-MARCH-02
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP
MP10 | 5 | 19:53 | 20:13 | 900 | 300 | 20:00 | NOTE_41 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.2167 | 20 | 13
KP76 | 5 | 20:13 | 20:33 | 900 | 300 | 20:20 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.55 | 20 | 33
OC102 | 5 | 20:33 | 20:54 | 1200 | 60 | 20:43 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 20.9 | 20 | 54
OC107 | 4 | 20:54 | 21:15 | 1200 | 60 | 21:04 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.25 | 21 | 15
OC121 | 4 | 21:15 | 21:36 | 1200 | 60 | 21:25 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.6 | 21 | 36
OC127 | 5 | 21:36 | 21:57 | 1200 | 60 | 21:46 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.95 | 21 | 57
OC128 | 5 | 21:57 | 22:18 | 1200 | 60 | 22:07 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.3 | 22 | 18
OC129 | 5 | 22:18 | 22:39 | 1200 | 60 | 22:28 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.65 | 22 | 39
OC133 | 4 | 22:39 | 23:00 | 1200 | 60 | 22:49 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23 | 23 | 0
OC134 | 3 | 23:00 | 23:21 | 1200 | 60 | 23:10 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.35 | 23 | 21
OC135 | 3 | 23:21 | 23:42 | 1200 | 60 | 23:31 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.7 | 23 | 42
OC136 | 3 | 23:42 | 0:03 | 1200 | 60 | 23:52 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 24.05 | 24 | 3
OC102 | 5 | 0:03 | 0:28 | 1200 | 300 | 0:13 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0.46667 | 0 | 28
MP34 | 5 | 0:28 | 0:48 | 900 | 300 | 0:35 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0.8 | 0 | 48
KP76 | 5 | 0:48 | 1:08 | 900 | 300 | 0:55 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.1333 | 1 | 8
KP26 | 5 | 1:08 | 1:28 | 900 | 300 | 1:15 | NOTE_10 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.4667 | 1 | 28
KP63 | 4 | 1:28 | 1:48 | 900 | 300 | 1:35 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.8 | 1 | 48
M102 | 5 | 1:48 | 2:08 | 900 | 300 | 1:55 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.1333 | 2 | 8
M85 | 5 | 2:08 | 2:28 | 900 | 300 | 2:15 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.4667 | 2 | 28
M90 | 5 | 2:28 | 2:48 | 900 | 300 | 2:35 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.8 | 2 | 48
M75 | 5 | 2:48 | 3:08 | 900 | 300 | 2:55 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 3.1333 | 3 | 8
M104 | 5 | 3:08 | 3:28 | 900 | 300 | 3:15 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 3.4667 | 3 | 28
[7 empty] | TOTAL | 0 | 6000 | 4800 | 2400 | 14100 | 0 | 0

## 2014-MARCH-03
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP
MP10 | 5 | 19:54 | 20:14 | 900 | 300 | 20:01 | NOTE_41 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.2333 | 20 | 14
KP76 | 5 | 20:14 | 20:34 | 900 | 300 | 20:21 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.5667 | 20 | 34
OC102 | 5 | 20:34 | 20:55 | 1200 | 60 | 20:44 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 20.9167 | 20 | 55
OC116 | 4 | 20:55 | 21:16 | 1200 | 60 | 21:05 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.2667 | 21 | 16
OC123 | 4 | 21:16 | 21:37 | 1200 | 60 | 21:26 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.6167 | 21 | 37
OC124 | 5 | 21:37 | 21:58 | 1200 | 60 | 21:47 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.9667 | 21 | 58
OC125 | 5 | 21:58 | 22:19 | 1200 | 60 | 22:08 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.3167 | 22 | 19
OC126 | 5 | 22:19 | 22:40 | 1200 | 60 | 22:29 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.6667 | 22 | 40
OC130 | 4 | 22:40 | 23:01 | 1200 | 60 | 22:50 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.0167 | 23 | 1
OC131 | 4 | 23:01 | 23:22 | 1200 | 60 | 23:11 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.3667 | 23 | 22
OC132 | 4 | 23:22 | 23:43 | 1200 | 60 | 23:32 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.7167 | 23 | 43
OC102 | 5 | 23:43 | 0:08 | 1200 | 300 | 23:53 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 24.1333 | 24 | 8
MP34 | 5 | 0:08 | 0:28 | 900 | 300 | 0:15 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0.46667 | 0 | 28
KP26 | 5 | 0:28 | 0:48 | 900 | 300 | 0:35 | NOTE_10 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0.8 | 0 | 48
KP76 | 5 | 0:48 | 1:08 | 900 | 300 | 0:55 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.1333 | 1 | 8
KP63 | 4 | 1:08 | 1:28 | 900 | 300 | 1:15 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.4667 | 1 | 28
M102 | 5 | 1:28 | 1:48 | 900 | 300 | 1:35 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 1.8 | 1 | 48
M85 | 5 | 1:48 | 2:08 | 900 | 300 | 1:55 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.1333 | 2 | 8
M90 | 5 | 2:08 | 2:28 | 900 | 300 | 2:15 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.4667 | 2 | 28
M75 | 5 | 2:28 | 2:48 | 900 | 300 | 2:35 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.8 | 2 | 48
M104 | 5 | 2:48 | 3:08 | 900 | 300 | 2:55 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 3.1333 | 3 | 8
KP64 | 4 | 3:08 | 3:28 | 900 | 300 | 3:15 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 3.4667 | 3 | 28
[7 empty] | TOTAL | 0 | 6000 | 6000 | 2400 | 12840 | 0 | 0

## 2014-MARCH-04
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP
MP11 | 4 | 19:55 | 20:15 | 900 | 300 | 20:02 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.25 | 20 | 15
KP76 | 5 | 20:15 | 20:35 | 900 | 300 | 20:22 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.5833 | 20 | 35
OC102 | 5 | 20:35 | 20:56 | 1200 | 60 | 20:45 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 20.9333 | 20 | 56
OC107 | 4 | 20:56 | 21:17 | 1200 | 60 | 21:06 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.2833 | 21 | 17
OC121 | 4 | 21:17 | 21:38 | 1200 | 60 | 21:27 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.6333 | 21 | 38
OC124 | 5 | 21:38 | 21:59 | 1200 | 60 | 21:48 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.9833 | 21 | 59
OC125 | 5 | 21:59 | 22:20 | 1200 | 60 | 22:09 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.3333 | 22 | 20
OC126 | 5 | 22:20 | 22:41 | 1200 | 60 | 22:30 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.6833 | 22 | 41
OC130 | 4 | 22:41 | 23:02 | 1200 | 60 | 22:51 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.0333 | 23 | 2
OC131 | 4 | 23:02 | 23:23 | 1200 | 60 | 23:12 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.3833 | 23 | 23
OC132 | 4 | 23:23 | 23:44 | 1200 | 60 | 23:33 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.7333 | 23 | 44
OC102 | 5 | 23:44 | 0:09 | 1200 | 300 | 23:54 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 24.15 | 24 | 9
MP34 | 5 | 0:09 | 0:29 | 900 | 300 | 0:16 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0.48333 | 0 | 29
KP57 | 4 | 0:29 | 0:49 | 900 | 300 | 0:36 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0.81667 | 0 | 49
KP26 | 5 | 0:49 | 1:09 | 900 | 300 | 0:56 | NOTE_10 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.15 | 1 | 9
KP63 | 4 | 1:09 | 1:29 | 900 | 300 | 1:16 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.4833 | 1 | 29
KP64 | 4 | 1:29 | 1:49 | 900 | 300 | 1:36 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.8167 | 1 | 49
M102 | 5 | 1:49 | 2:09 | 900 | 300 | 1:56 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.15 | 2 | 9
M85 | 5 | 2:09 | 2:29 | 900 | 300 | 2:16 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.4833 | 2 | 29
M90 | 5 | 2:29 | 2:49 | 900 | 300 | 2:36 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.8167 | 2 | 49
M104 | 5 | 2:49 | 3:09 | 900 | 300 | 2:56 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 3.15 | 3 | 9
MP49 | 5 | 3:09 | 3:29 | 900 | 300 | 3:16 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 3.4833 | 3 | 29
[7 empty] | TOTAL | 0 | 4800 | 6000 | 3600 | 12840 | 0 | 0

## 2014-MARCH-05
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP
MP14 | 4 | 19:55 | 20:10 | 600 | 300 | 20:00 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 20.1667 | 20 | 10
KP76 | 5 | 20:10 | 20:30 | 900 | 300 | 20:17 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.5 | 20 | 30
KP2 | 4 | 20:30 | 20:50 | 900 | 300 | 20:37 | NOTE_04 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.8333 | 20 | 50
KP57 | 4 | 20:50 | 21:05 | 600 | 300 | 20:55 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 21.0833 | 21 | 5
OC102 | 5 | 21:05 | 21:26 | 1200 | 60 | 21:15 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.4333 | 21 | 26
OC116 | 4 | 21:26 | 21:47 | 1200 | 60 | 21:36 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.7833 | 21 | 47
OC123 | 4 | 21:47 | 22:08 | 1200 | 60 | 21:57 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.1333 | 22 | 8
OC127 | 5 | 22:08 | 22:29 | 1200 | 60 | 22:18 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.4833 | 22 | 29
OC128 | 5 | 22:29 | 22:50 | 1200 | 60 | 22:39 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.8333 | 22 | 50
OC129 | 5 | 22:50 | 23:11 | 1200 | 60 | 23:00 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.1833 | 23 | 11
OC133 | 4 | 23:11 | 23:32 | 1200 | 60 | 23:21 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.5333 | 23 | 32
OC134 | 3 | 23:32 | 23:53 | 1200 | 60 | 23:42 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.8833 | 23 | 53
OC135 | 3 | 23:53 | 0:14 | 1200 | 60 | 0:03 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 24.2333 | 24 | 14
OC136 | 3 | 0:14 | 0:35 | 1200 | 60 | 0:24 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 0.58333 | 0 | 35
OC102 | 5 | 0:35 | 1:00 | 1200 | 300 | 0:45 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1 | 1 | 0
MP34 | 5 | 1:00 | 1:20 | 900 | 300 | 1:07 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 1.3333 | 1 | 20
KP63 | 4 | 1:20 | 1:40 | 900 | 300 | 1:27 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.6667 | 1 | 40
KP64 | 4 | 1:40 | 2:00 | 900 | 300 | 1:47 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 2 | 2 | 0
M102 | 5 | 2:00 | 2:20 | 900 | 300 | 2:07 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.3333 | 2 | 20
M85 | 5 | 2:20 | 2:40 | 900 | 300 | 2:27 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.6667 | 2 | 40
M90 | 5 | 2:40 | 3:00 | 900 | 300 | 2:47 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
M104 | 5 | 3:00 | 3:20 | 900 | 300 | 3:07 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 3.3333 | 3 | 20
[7 empty] | TOTAL | 0 | 4800 | 5700 | 2100 | 14100 | 0 | 0

## 2014-MARCH-06
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP
MP14 | 4 | 19:56 | 20:16 | 900 | 300 | 20:03 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.2667 | 20 | 16
KP76 | 5 | 20:16 | 20:36 | 900 | 300 | 20:23 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.6 | 20 | 36
KP57 | 4 | 20:36 | 20:51 | 600 | 300 | 20:41 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 20.85 | 20 | 51
OC102 | 5 | 20:51 | 21:12 | 1200 | 60 | 21:01 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.2 | 21 | 12
OC107 | 4 | 21:12 | 21:33 | 1200 | 60 | 21:22 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.55 | 21 | 33
OC121 | 4 | 21:33 | 21:54 | 1200 | 60 | 21:43 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.9 | 21 | 54
OC124 | 5 | 21:54 | 22:15 | 1200 | 60 | 22:04 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.25 | 22 | 15
OC125 | 5 | 22:15 | 22:36 | 1200 | 60 | 22:25 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.6 | 22 | 36
OC126 | 5 | 22:36 | 22:57 | 1200 | 60 | 22:46 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.95 | 22 | 57
OC130 | 4 | 22:57 | 23:18 | 1200 | 60 | 23:07 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.3 | 23 | 18
OC131 | 4 | 23:18 | 23:39 | 1200 | 60 | 23:28 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.65 | 23 | 39
OC132 | 4 | 23:39 | 0:00 | 1200 | 60 | 23:49 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 24 | 24 | 0
OC102 | 5 | 0:00 | 0:25 | 1200 | 300 | 0:10 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0.41667 | 0 | 25
KP21 | 4 | 0:25 | 0:45 | 900 | 300 | 0:32 | NOTE_10; NOTE_11 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0.75 | 0 | 45
KP27 | 4 | 0:45 | 1:05 | 900 | 300 | 0:52 | NOTE_10 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.0833 | 1 | 5
MP34 | 5 | 1:05 | 1:25 | 900 | 300 | 1:12 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 1.4167 | 1 | 25
KP63 | 4 | 1:25 | 1:45 | 900 | 300 | 1:32 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.75 | 1 | 45
KP64 | 4 | 1:45 | 2:05 | 900 | 300 | 1:52 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 2.0833 | 2 | 5
M102 | 5 | 2:05 | 2:25 | 900 | 300 | 2:12 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.4167 | 2 | 25
M85 | 5 | 2:25 | 2:45 | 900 | 300 | 2:32 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.75 | 2 | 45
M90 | 5 | 2:45 | 3:05 | 900 | 300 | 2:52 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 3.0833 | 3 | 5
M104 | 5 | 3:05 | 3:25 | 900 | 300 | 3:12 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 3.4167 | 3 | 25
[7 empty] | TOTAL | 0 | 4800 | 6900 | 2400 | 12840 | 0 | 0

## 2014-MARCH-07
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP
KP76 | 5 | 19:56 | 20:16 | 900 | 300 | 20:03 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.2667 | 20 | 16
KP57 | 4 | 20:16 | 20:36 | 900 | 300 | 20:23 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.6 | 20 | 36
OC127 | 5 | 20:36 | 20:57 | 1200 | 60 | 20:46 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 20.95 | 20 | 57
OC128 | 5 | 20:57 | 21:18 | 1200 | 60 | 21:07 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.3 | 21 | 18
OC129 | 5 | 21:18 | 21:43 | 1200 | 300 | 21:28 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 21.7167 | 21 | 43
M85 | 5 | 21:43 | 22:03 | 900 | 300 | 21:50 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 22.05 | 22 | 3
KP25 | 2 | 22:03 | 22:23 | 900 | 300 | 22:10 | NOTE_10 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 22.3833 | 22 | 23
RML19 | 5 | 22:23 | 22:34 | 600 | 60 | 22:28 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5667 | 22 | 34
RML19 | 5 | 22:34 | 22:45 | 600 | 60 | 22:39 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 22.75 | 22 | 45
RML19 | 5 | 22:45 | 22:56 | 600 | 60 | 22:50 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 22.9333 | 22 | 56
RML19 | 5 | 22:56 | 23:07 | 600 | 60 | 23:01 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 23.1167 | 23 | 7
RML19 | 5 | 23:07 | 23:18 | 600 | 60 | 23:12 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 23.3 | 23 | 18
RML19 | 5 | 23:18 | 23:29 | 600 | 60 | 23:23 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 23.4833 | 23 | 29
RML19 | 5 | 23:29 | 23:40 | 600 | 60 | 23:34 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 23.6667 | 23 | 40
RML19 | 5 | 23:40 | 23:51 | 600 | 60 | 23:45 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 23.85 | 23 | 51
RML19 | 5 | 23:51 | 0:02 | 600 | 60 | 23:56 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 24.0333 | 24 | 2
RML19 | 5 | 0:02 | 0:13 | 600 | 60 | 0:07 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21667 | 0 | 13
RML19 | 5 | 0:13 | 0:24 | 600 | 60 | 0:18 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 24
RML19 | 5 | 0:24 | 0:35 | 600 | 60 | 0:29 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58333 | 0 | 35
RML19 | 5 | 0:35 | 0:46 | 600 | 60 | 0:40 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76667 | 0 | 46
RML19 | 5 | 0:46 | 0:57 | 600 | 60 | 0:51 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 57
RML19 | 5 | 0:57 | 1:08 | 600 | 60 | 1:02 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1333 | 1 | 8
RML19 | 5 | 1:08 | 1:19 | 600 | 60 | 1:13 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3167 | 1 | 19
RML19 | 5 | 1:19 | 1:30 | 600 | 60 | 1:24 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1 | 30
RML19 | 5 | 1:30 | 1:41 | 600 | 60 | 1:35 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6833 | 1 | 41
RML19 | 5 | 1:41 | 1:52 | 600 | 60 | 1:46 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8667 | 1 | 52
RML19 | 5 | 1:52 | 2:03 | 600 | 60 | 1:57 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 2.05 | 2 | 3
RML19 | 5 | 2:03 | 2:14 | 600 | 60 | 2:08 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2333 | 2 | 14
RML19 | 5 | 2:14 | 2:25 | 600 | 60 | 2:19 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4167 | 2 | 25
RML19 | 5 | 2:25 | 2:36 | 600 | 60 | 2:30 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 2 | 36
RML19 | 5 | 2:36 | 2:47 | 600 | 60 | 2:41 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7833 | 2 | 47
RML19 | 5 | 2:47 | 2:58 | 600 | 60 | 2:52 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9667 | 2 | 58
RML19 | 5 | 2:58 | 3:09 | 600 | 60 | 3:03 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 3.15 | 3 | 9
RML19 | 5 | 3:09 | 3:20 | 600 | 60 | 3:14 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3333 | 3 | 20
RML19 | 5 | 3:20 | 3:31 | 600 | 60 | 3:25 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5167 | 3 | 31
RML19 | 5 | 3:31 | 3:42 | 600 | 60 | 3:36 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7 | 3 | 42
RML19 | 5 | 3:42 | 3:53 | 600 | 60 | 3:47 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8833 | 3 | 53
RML19 | 5 | 3:53 | 4:04 | 600 | 60 | 3:58 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0667 | 4 | 4
RML19 | 5 | 4:04 | 4:15 | 600 | 60 | 4:09 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 4.25 | 4 | 15
RML19 | 5 | 4:15 | 4:26 | 600 | 60 | 4:20 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4333 | 4 | 26
RML19 | 5 | 4:26 | 4:37 | 600 | 60 | 4:31 | NOTE_10 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6167 | 4 | 37
RML19 | 5 | 4:37 | 4:52 | 600 | 300 | 4:42 | NOTE_10 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8667 | 4 | 52
MP34 | 5 | 4:52 | 5:08 | 900 | 60 | 4:59 |  | 0 | 0 | 0 | 960 | 0 | 0 | 0 | 5.1333 | 5 | 8
KP32 | 4 | 5:08 | 5:24 | 900 | 60 | 5:15 |  | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 5.4 | 5 | 24
M104 | 5 | 5:24 | 5:40 | 900 | 60 | 5:31 |  | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 5.6667 | 5 | 40
M90 | 5 | 5:40 | 5:56 | 900 | 60 | 5:47 |  | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 5.9333 | 5 | 56
KP41 | 3 | 5:56 | 6:12 | 900 | 60 | 6:03 |  | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 6.2 | 6 | 12
KP74 | 5 | 6:12 | 6:23 | 600 | 60 | 6:17 |  | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 6.3833 | 6 | 23
[7 empty] | TOTAL | 23340 | 3120 | 6180 | 960 | 4020 | 0 | 0

## 2014-MARCH-08
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP
MP25 | 4 | 19:57 | 20:12 | 600 | 300 | 20:02 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 20.2 | 20 | 12
KP76 | 5 | 20:12 | 20:32 | 900 | 300 | 20:19 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.5333 | 20 | 32
OC107 | 4 | 20:32 | 20:53 | 1200 | 60 | 20:42 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 20.8833 | 20 | 53
OC116 | 4 | 20:53 | 21:14 | 1200 | 60 | 21:03 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.2333 | 21 | 14
OC121 | 4 | 21:14 | 21:35 | 1200 | 60 | 21:24 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.5833 | 21 | 35
OC123 | 4 | 21:35 | 21:56 | 1200 | 60 | 21:45 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.9333 | 21 | 56
OC127 | 5 | 21:56 | 22:17 | 1200 | 60 | 22:06 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.2833 | 22 | 17
OC128 | 5 | 22:17 | 22:38 | 1200 | 60 | 22:27 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.6333 | 22 | 38
OC129 | 5 | 22:38 | 22:59 | 1200 | 60 | 22:48 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.9833 | 22 | 59
OC133 | 4 | 22:59 | 23:20 | 1200 | 60 | 23:09 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.3333 | 23 | 20
OC134 | 3 | 23:20 | 23:41 | 1200 | 60 | 23:30 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 23.6833 | 23 | 41
OC135 | 3 | 23:41 | 0:02 | 1200 | 60 | 23:51 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 24.0333 | 24 | 2
OC136 | 3 | 0:02 | 0:27 | 1200 | 300 | 0:12 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0.45 | 0 | 27
KP76 | 5 | 0:27 | 0:47 | 900 | 300 | 0:34 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0.78333 | 0 | 47
MP34 | 5 | 0:47 | 1:07 | 900 | 300 | 0:54 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 1.1167 | 1 | 7
KP64 | 4 | 1:07 | 1:27 | 900 | 300 | 1:14 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.45 | 1 | 27
M102 | 5 | 1:27 | 1:47 | 900 | 300 | 1:34 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 1.7833 | 1 | 47
M85 | 5 | 1:47 | 2:07 | 900 | 300 | 1:54 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.1167 | 2 | 7
M90 | 5 | 2:07 | 2:27 | 900 | 300 | 2:14 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.45 | 2 | 27
M104 | 5 | 2:27 | 2:47 | 900 | 300 | 2:34 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.7833 | 2 | 47
MP49 | 5 | 2:47 | 3:07 | 900 | 300 | 2:54 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 3.1167 | 3 | 7
M75 | 5 | 3:07 | 3:27 | 900 | 300 | 3:14 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 3.45 | 3 | 27
[7 empty] | TOTAL | 0 | 6000 | 3600 | 3300 | 14100 | 0 | 0

## 2014-MARCH-09
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP
MP25 | 4 | 19:58 | 20:13 | 600 | 300 | 20:03 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 20.2167 | 20 | 13
KP55 | 3 | 20:13 | 20:28 | 600 | 300 | 20:18 |  | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 20.4667 | 20 | 28
KP76 | 5 | 20:28 | 20:48 | 900 | 300 | 20:35 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.8 | 20 | 48
M30 | 4 | 20:48 | 21:09 | 1200 | 60 | 20:58 |  | 0 | 1260 | 0 | 0 | 0 | 0 | 0 | 21.15 | 21 | 9
OC123 | 4 | 21:09 | 21:30 | 1200 | 60 | 21:19 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.5 | 21 | 30
OC124 | 5 | 21:30 | 21:51 | 1200 | 60 | 21:40 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 21.85 | 21 | 51
OC125 | 5 | 21:51 | 22:12 | 1200 | 60 | 22:01 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.2 | 22 | 12
OC126 | 5 | 22:12 | 22:33 | 1200 | 60 | 22:22 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.55 | 22 | 33
OC130 | 4 | 22:33 | 22:54 | 1200 | 60 | 22:43 |  | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 22.9 | 22 | 54
OC131 | 4 | 22:54 | 23:19 | 1200 | 300 | 23:04 |  | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 23.3167 | 23 | 19
OC132 | 4 | 23:19 | 23:39 | 900 | 300 | 23:26 |  | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 23.65 | 23 | 39
KP63 | 4 | 23:39 | 23:59 | 900 | 300 | 23:46 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 23.9833 | 23 | 59
KP26 | 5 | 23:59 | 0:19 | 900 | 300 | 0:06 | NOTE_10 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 24.3167 | 24 | 19
MP34 | 5 | 0:19 | 0:39 | 900 | 300 | 0:26 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0.65 | 0 | 39
KP64 | 4 | 0:39 | 0:59 | 900 | 300 | 0:46 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0.98333 | 0 | 59
M102 | 5 | 0:59 | 1:19 | 900 | 300 | 1:06 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 1.3167 | 1 | 19
KP73 | 3 | 1:19 | 1:39 | 900 | 300 | 1:26 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.65 | 1 | 39
M85 | 5 | 1:39 | 1:59 | 900 | 300 | 1:46 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 1.9833 | 1 | 59
M90 | 5 | 1:59 | 2:19 | 900 | 300 | 2:06 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.3167 | 2 | 19
KP36 | 2 | 2:19 | 2:39 | 900 | 300 | 2:26 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 2.65 | 2 | 39
M104 | 5 | 2:39 | 2:59 | 900 | 300 | 2:46 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.9833 | 2 | 59
MP49 | 5 | 2:59 | 3:19 | 900 | 300 | 3:06 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 3.3167 | 3 | 19
M75 | 5 | 3:19 | 3:39 | 900 | 300 | 3:26 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 3.65 | 3 | 39
[7 empty] | TOTAL | 0 | 7260 | 8100 | 3300 | 9000 | 0 | 0

## 2014-MARCH-10
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP
MP25 | 4 | 19:58 | 20:13 | 600 | 300 | 20:03 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 20.2167 | 20 | 13
MP24 | 3 | 20:13 | 20:33 | 900 | 300 | 20:20 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.55 | 20 | 33
KP2 | 4 | 20:33 | 20:53 | 900 | 300 | 20:40 | NOTE_04 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.8833 | 20 | 53
MP11 | 4 | 20:53 | 21:13 | 900 | 300 | 21:00 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 21.2167 | 21 | 13
KP76 | 5 | 21:13 | 21:33 | 900 | 300 | 21:20 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 21.55 | 21 | 33
MP12 | 4 | 21:33 | 21:48 | 600 | 300 | 21:38 |  | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 21.8 | 21 | 48
M30 | 4 | 21:48 | 22:08 | 900 | 300 | 21:55 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 22.1333 | 22 | 8
KP27 | 4 | 22:08 | 22:28 | 900 | 300 | 22:15 | NOTE_10 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 22.4667 | 22 | 28
MP34 | 5 | 22:28 | 22:48 | 900 | 300 | 22:35 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 22.8 | 22 | 48
KP64 | 4 | 22:48 | 23:08 | 900 | 300 | 22:55 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 23.1333 | 23 | 8
KP26 | 5 | 23:08 | 23:28 | 900 | 300 | 23:15 | NOTE_10 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 23.4667 | 23 | 28
M102 | 5 | 23:28 | 23:48 | 900 | 300 | 23:35 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 23.8 | 23 | 48
M85 | 5 | 23:48 | 0:08 | 900 | 300 | 23:55 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 24.1333 | 24 | 8
M90 | 5 | 0:08 | 0:28 | 900 | 300 | 0:15 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0.46667 | 0 | 28
KP20 | 2 | 0:28 | 0:48 | 900 | 300 | 0:35 | NOTE_10 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0.8 | 0 | 48
KP24 | 1 | 0:48 | 1:08 | 900 | 300 | 0:55 | NOTE_10 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.1333 | 1 | 8
M82 | 4 | 1:08 | 1:28 | 900 | 300 | 1:15 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 1.4667 | 1 | 28
KP7 | 4 | 1:28 | 1:48 | 900 | 300 | 1:35 | NOTE_09 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1.8 | 1 | 48
M104 | 5 | 1:48 | 2:08 | 900 | 300 | 1:55 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.1333 | 2 | 8
M75 | 5 | 2:08 | 2:28 | 900 | 300 | 2:15 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.4667 | 2 | 28
M86 | 5 | 2:28 | 2:48 | 900 | 300 | 2:35 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.8 | 2 | 48
M87 | 5 | 2:48 | 3:08 | 900 | 300 | 2:55 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 3.1333 | 3 | 8
MP49 | 5 | 3:08 | 3:28 | 900 | 300 | 3:15 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 3.4667 | 3 | 28
KP44 | 2 | 3:28 | 3:48 | 900 | 300 | 3:35 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 3.8 | 3 | 48
[7 empty] | TOTAL | 0 | 10800 | 10800 | 6600 | 0 | 0 | 0

## 2014-MARCH-11
CODE | PRIORITY | UT(0) | UT(1) | EXPT | OverHeads | EPOCH | NOTES | TIME RML | TIME M | TIME KP | TIME MP | TIME OC | TIME AS | TIME IP
MP25 | 4 | 19:59 | 20:19 | 900 | 300 | 20:06 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.3167 | 20 | 19
MP24 | 3 | 20:19 | 20:39 | 900 | 300 | 20:26 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 20.65 | 20 | 39
KP2 | 4 | 20:39 | 20:59 | 900 | 300 | 20:46 | NOTE_04 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 20.9833 | 20 | 59
MP11 | 4 | 20:59 | 21:19 | 900 | 300 | 21:06 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 21.3167 | 21 | 19
M30 | 4 | 21:19 | 21:39 | 900 | 300 | 21:26 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 21.65 | 21 | 39
RML17 | 5 | 21:39 | 21:50 | 600 | 60 | 21:44 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 21.8333 | 21 | 50
RML17 | 5 | 21:50 | 22:01 | 600 | 60 | 21:55 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 22.0167 | 22 | 1
RML17 | 5 | 22:01 | 22:12 | 600 | 60 | 22:06 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 22.2 | 22 | 12
RML17 | 5 | 22:12 | 22:23 | 600 | 60 | 22:17 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 22.3833 | 22 | 23
RML17 | 5 | 22:23 | 22:34 | 600 | 60 | 22:28 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5667 | 22 | 34
RML17 | 5 | 22:34 | 22:45 | 600 | 60 | 22:39 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 22.75 | 22 | 45
RML17 | 5 | 22:45 | 22:56 | 600 | 60 | 22:50 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 22.9333 | 22 | 56
RML17 | 5 | 22:56 | 23:07 | 600 | 60 | 23:01 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 23.1167 | 23 | 7
RML17 | 5 | 23:07 | 23:18 | 600 | 60 | 23:12 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 23.3 | 23 | 18
RML17 | 5 | 23:18 | 23:29 | 600 | 60 | 23:23 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 23.4833 | 23 | 29
RML17 | 5 | 23:29 | 23:40 | 600 | 60 | 23:34 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 23.6667 | 23 | 40
RML17 | 5 | 23:40 | 23:51 | 600 | 60 | 23:45 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 23.85 | 23 | 51
RML17 | 5 | 23:51 | 0:02 | 600 | 60 | 23:56 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 24.0333 | 24 | 2
RML17 | 5 | 0:02 | 0:13 | 600 | 60 | 0:07 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21667 | 0 | 13
RML17 | 5 | 0:13 | 0:24 | 600 | 60 | 0:18 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 24
RML17 | 5 | 0:24 | 0:35 | 600 | 60 | 0:29 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58333 | 0 | 35
RML17 | 5 | 0:35 | 0:46 | 600 | 60 | 0:40 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76667 | 0 | 46
RML17 | 5 | 0:46 | 0:57 | 600 | 60 | 0:51 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 57
RML17 | 5 | 0:57 | 1:08 | 600 | 60 | 1:02 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1333 | 1 | 8
RML17 | 5 | 1:08 | 1:19 | 600 | 60 | 1:13 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3167 | 1 | 19
RML17 | 5 | 1:19 | 1:30 | 600 | 60 | 1:24 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1 | 30
RML17 | 5 | 1:30 | 1:41 | 600 | 60 | 1:35 |  | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6833 | 1 | 41
RML17 | 5 | 1:41 | 1:56 | 600 | 300 | 1:46 |  | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9333 | 1 | 56
KP76 | 5 | 1:56 | 2:16 | 900 | 300 | 2:03 | NOTE_36; NOTE_12 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 2.2667 | 2 | 16
M102 | 5 | 2:16 | 2:36 | 900 | 300 | 2:23 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 2.6 | 2 | 36
KP25 | 2 | 2:36 | 2:56 | 900 | 300 | 2:43 | NOTE_10 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 2.9333 | 2 | 56
KP4 | 1 | 2:56 | 3:16 | 900 | 300 | 3:03 | NOTE_06 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 3.2667 | 3 | 16
KP73 | 3 | 3:16 | 3:36 | 900 | 300 | 3:23 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 3.6 | 3 | 36
MP34 | 5 | 3:36 | 3:56 | 900 | 300 | 3:43 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 3.9333 | 3 | 56
M85 | 5 | 3:56 | 4:16 | 900 | 300 | 4:03 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 4.2667 | 4 | 16
M90 | 5 | 4:16 | 4:36 | 900 | 300 | 4:23 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 4.6 | 4 | 36
KP32 | 4 | 4:36 | 4:56 | 900 | 300 | 4:43 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 4.9333 | 4 | 56
KP74 | 5 | 4:56 | 5:16 | 900 | 300 | 5:03 |  | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 5.2667 | 5 | 16
M104 | 5 | 5:16 | 5:36 | 900 | 300 | 5:23 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 5.6 | 5 | 36
KP7 | 4 | 5:36 | 5:56 | 900 | 300 | 5:43 | NOTE_09 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 5.9333 | 5 | 56
M82 | 4 | 5:56 | 6:16 | 900 | 300 | 6:03 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6.2667 | 6 | 16
M75 | 5 | 6:16 | 6:36 | 900 | 300 | 6:23 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6.6 | 6 | 36
M86 | 5 | 6:36 | 6:56 | 900 | 300 | 6:43 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6.9333 | 6 | 56
M87 | 5 | 6:56 | 7:16 | 900 | 300 | 7:03 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 7.2667 | 7 | 16
[7 empty] | TOTAL | 15420 | 10800 | 9600 | 4800 | 0 | 0 | 0

## APPENDIX A
OBJECT | PRIORITY | REQ OBS | 2014-MAR-02 | 2014-MAR-03 | 2014-MAR-04 | 2014-MAR-05 | 2014-MAR-06 | 2014-MAR-07 | 2014-MAR-08 | 2014-MAR-09 | 2014-MAR-10 | 2014-MAR-11 | 2014-MAR-30 | 2014-MAR-31 | PROG. OBS | DIFF
MP10 | 5 | 10 | 1 | 1 | MOON | MOON | MOON | MOON | MOON | 0 | 0 | 0 | 0 | 0 | 2 | -8
MP34 | 5 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 10 | 0
MP49 | 5 | 10 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 4 | -6
MP11 | 4 | 4 | 0 | 0 | 1 | MOON | MOON | MOON | MOON | 0 | 1 | 1 | 0 | 0 | 3 | -1
MP12 | 4 | 4 | 0 | 0 | 0 | MOON | MOON | MOON | MOON | 0 | 1 | 0 | 0 | 0 | 1 | -3
MP13 | 4 | 4 | 0 | 0 | 0 | MOON | MOON | MOON | MOON | 0 | 0 | 0 | 0 | 0 | 0 | -4
MP14 | 4 | 4 | 0 | 0 | 0 | 1 | 1 | MOON | MOON | MOON | MOON | MOON | 0 | 0 | 2 | -2
MP25 | 4 | 4 | 0 | MOON | MOON | MOON | MOON | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 4 | 0
MP26 | 4 | 4 | 0 | 0 | MOON | MOON | MOON | MOON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
MP27 | 4 | 4 | 0 | 0 | 0 | 0 | MOON | MOON | MOON | MOON | MOON | 0 | 0 | 0 | 0 | -4
MP28 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | MOON | MOON | MOON | MOON | MOON | 0 | 0 | 0 | -4
MP29 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | MOON | MOON | MOON | MOON | 0 | 0 | 0 | -4
MP30 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | MOON | MOON | MOON | MOON | 0 | 0 | 0 | -4
MP33 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
MP35 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
MP37 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
MP38 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
MP40 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
MP41 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
MP42 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
MP45 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
MP48 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
MP24 | 3 | 2 | 0 | MOON | MOON | MOON | MOON | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0
MP31 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP39 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP43 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP44 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP47 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
MP50 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M85 | 5 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 10 | 0
M75 | 5 | 10 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | -4
M86 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | -8
M87 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | -8
M102 | 5 | 10 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 9 | -1
M90 | 5 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 10 | 0
M104 | 5 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 10 | 0
M17 | 4 | 4 | HOR | HOR | HOR | HOR | HOR | HOR | HOR | HOR | HOR | HOR | HOR | HOR | 0 | -4
M30 | 4 | 4 | 0 | 0 | 0 | MOON | MOON | MOON | MOON | 1 | 1 | 1 | 0 | 0 | 3 | -1
M82 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | -2
M91 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
M33 | 4 | 4 | 0 | 0 | MOON | MOON | MOON | MOON | MOON | 0 | 0 | 0 | 0 | 0 | 0 | -4
M92 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
M76 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M34 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M44 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M77 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M74 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M36 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M105 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M97 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M100 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M101 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M89 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
M53 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1
M88 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1
M47 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MOON | MOON | 0 | 0 | 0 | 0 | -1
M79 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1
RML19 | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0
RML17 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 23 | 23
RML20 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KP76 | 5 | 13 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 13 | 0
KP74 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0
KP55 | 3 | 1 | 0 | 0 | 0 | MOON | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
KP57 | 4 | 5 | 0 | 0 | 1 | 1 | 1 | 1 | MOON | MOON | MOON | MOON | 0 | 0 | 4 | -1
KP59 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MOON | MOON | 0 | 0 | 0 | -5
KP63 | 4 | 6 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
KP64 | 4 | 6 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 7 | 1
KP5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MOON | MOON | 0 | 0 | 0 | -4
KP7 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | -2
KP3 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5
KP32 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0
KP1 | 1 | 0 | 0 | 0 | 0 | MOON | MOON | MOON | MOON | 0 | 0 | 0 | 0 | 0 | 0 | 0
KP2 | 4 | 3 | 0 | 0 | 0 | 1 | 0 | MOON | MOON | MOON | 1 | 1 | 0 | 0 | 3 | 0
KP4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1
KP65 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
KP13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KP15 | 1 | 0 | 0 | 0 | TRA | MOON | MOON | MOON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KP16 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | TRA | 0 | 0 | 0 | 0 | 0 | 0 | -1
KP17 | 1 | 1 | 0 | 0 | 0 | 0 | TRA | MOON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1
KP78 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
KP18 | 1 | 1 | 0 | 0 | TRA | TRA | TRA | MOON | MOON | MOON | MOON | MOON | 0 | 0 | 0 | -1
KP19 | 2 | 1 | 0 | 0 | 0 | 0 | TRA | 0 | MOON | MOON | MOON | MOON | 0 | 0 | 0 | -1
KP20 | 2 | 2 | 0 | 0 | TRA | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | -1
KP21 | 4 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | MOON | MOON | MOON | MOON | 0 | 0 | 1 | -1
KP22 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | TRA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1
KP23 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MOON | MOON | 0 | 0 | 0 | -1
KP24 | 1 | 1 | 0 | TRA | 0 | 0 | 0 | TRA | 0 | 0 | 1 | MOON | 0 | 0 | 1 | 0
KP25 | 2 | 1 | TRA | 0 | 0 | TRA | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 1
KP26 | 5 | 5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 5 | 0
KP27 | 4 | 2 | 0 | TRA | 0 | 0 | 1 | TRA | 0 | 0 | 1 | TRA | 0 | 0 | 2 | 0
KP79 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | TRA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4
KP73 | 3 | 1 | 0 | 0 | 0 | TRA | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 1
KP36 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
KP37 | 2 | 1 | 0 | TRA | 0 | 0 | 0 | 0 | 0 | 0 | TRA | 0 | 0 | 0 | 0 | -1
KP38 | 3 | 2 | 0 | 0 | 0 | TRA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2
KP39 | 2 | 1 | 0 | 0 | TRA | 0 | 0 | TRA | 0 | 0 | TRA | 0 | 0 | 0 | 0 | -1
KP40 | 4 | 3 | 0 | 0 | TRA | 0 | 0 | 0 | TRA | 0 | 0 | 0 | 0 | 0 | 0 | -3
KP41 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
KP42 | 1 | 1 | TRA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1
KP43 | 1 | 0 | 0 | 0 | TRA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KP44 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | TRA | 0 | 1 | 0 | 0 | 0 | 1 | 0
OC101 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC102 | 5 | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0
OC107 | 4 | 4 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
OC116 | 4 | 4 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | -1
OC118 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC119 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC120 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC121 | 4 | 4 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
OC122 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1
OC123 | 4 | 5 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | -1
OC124 | 5 | 5 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | -1
OC125 | 5 | 5 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | -1
OC126 | 5 | 5 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | -1
OC127 | 5 | 5 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | -1
OC128 | 5 | 5 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | -1
OC129 | 5 | 5 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | -1
OC130 | 4 | 5 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | -1
OC131 | 4 | 5 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | -1
OC132 | 4 | 5 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | -1
OC133 | 4 | 4 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | -1
OC134 | 3 | 4 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | -1
OC135 | 3 | 4 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | -1
OC136 | 3 | 4 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | -1

## APPENDIX B
NOTE | COMMENT | AUTHOR
NOTE_01 | Assuming an air mass of 1.6 and a seeing of 1.0 arcsec, the HARPS-S ETC indicates that a total exposure of about 30 min is required for SPI study purposes. In order to conduct a pilot study for the detection of oscillations, we ask to perform fast time series observations during 1-2 nights at the beginning of the monitoring campaign, under the supervision of a trained visiting observer (Francesco Borsa) . A sequence of 30 spectra, each with an exposure time of 60 seconds is adequate for this purpose. In case of seeing worse than 1.5 arcsec, the exposure time could be increased up to 90 second per spectrum taking a sequence of 15-20 spectra. Owing to the CCD reading time (about 30 seconds per reading), the overhead increases to about 15-20 minutes for these short-cadence sequences. The total exposure time (Texp*n Spectra) for each epoch is determined by the requirement of reaching S/N >~ 400 per pixel at 395 nm (continuum between the H and K CaII lines). | AMa
NOTE_02 | Assuming an air mass of 1.6 and a seeing of 1.0 arcsec, the HARPS-S ETC indicates that about 30 min per exposure are required. It is mandatory to avoid saturation at longer wavelength , therefore the total exposure time needs to be splitted in subexposures of max 2-5 min. However, optimal subexposure times and saturation thresholds depend on the actual seeing. A sub-exposure time of 180-200 seconds appears to be adequate for an air mass around 1.6 and an average seeing of 1.0 arcsec. The total exposure time (Texp*n Spectra) for each epoch is determined by the requirement of reaching S/N >~ 400 per pixel at 395 nm (continuum between the H and K CaII lines). In order to study SPI effects at a single epoch, a coverage of at least three orbital periods is recommended (at least 10 observations). Continuous monitoring (dayly observations) would provide the best information, but -- taking into account possible difficulties in scheduling 10 consecutive nights -- a uniform phase coverage of the 3.3d period for three times along a maximum time span of 2-3 weeks is an acceptable compromise. A longer time baseline is not recommended because the pattern of stellar active regions may undergo rearrangement. | AMa
NOTE_03 | LP Spread 40 obs. along the semester, Observation starting sinceAugust 7 to January 31. Max Epochs 56 planned epochs 40 | SDe
NOTE_04 | LP Spread 40 obs. along the semester, Observation starting since September 2 to January 31. Max Epochs 48 planned epochs 40 | SDe
NOTE_05 | LP Spread 31 obs. along the semester, Observation starting since September 28 to January 31. | SDe
NOTE_06 | LP Spread 18 obs. along the semester, Observation starting since November 2 to January 31. | SDe
NOTE_07 | LP Spread 10 obs. along the semester, Observation starting since December 26 to January 31. HD106515A binary system with similar components separation= 6.9 arcsec pos angle= 267 deg (from N to E) delta V =0.27 DO brightest (=eastern) component only; due the high possibility of contamination with bad seeing this sar shall be observed with seeingbetter that 1.5 arcsc | SDe/RCl
NOTE_08 | LP Spread 56 obs. along the semester, Observation starting since August 26 to January 31. | SDe
NOTE_09 | LP Spread 11 obs. along the semester, Observation starting since December 4 to January 31. | SDe
NOTE_10 | TP Spread over semester (1/month) | SDe
NOTE_11 | red companion at 6.86 arcsec, Delta R=1.36 mag. DO brighter | RCl
NOTE_12 | binary system with similar components separation= 31 arcsec pos angle= (from N to E) delta V =0.05 DO northern component only SEE NOTE_36 | RCl
NOTE_13 | binary system with similar components separation= 11.2 arcsec, pos angle= (from N to E) delta I = 0.53, DO secondary only | RCl
NOTE_14 | Do not observe during AOT27 (Mail by SDe 2013-Feb-02) | SDe
NOTE_15 | The target is a OC Target once it will be observed with other oCs target it will be not observed in KP program | SDe
NOTE_16 | This star has been rejected. See the Aso's Mail of 2012-10-18. | RCl
NOTE_17 | This M star has been REJECTED. See Gmi's Mail of 2012 Dec 7th | RCl
NOTE_18 | M33 (ap_566) -- Star in double system | LAf
NOTE_19 | M43 (ap_3378) -- Double or multiple star | LAf
NOTE_20 | M44 (ap_846) -- High proper motion star (stella molto spostata nella finding chart, rispetto alle coordinate) | LAf
NOTE_21 | M54 (ap_2649) -- Star in double system | LAf
NOTE_22 | M61 (ap_3093) -- Star in double system con M64 | LAf
NOTE_23 | M64 (ap_3092) -- Star in double system con M61 | LAf
NOTE_24 | M69 (ap_2844) -- X-ray source | LAf
NOTE_25 | It is the brightest star in the field | ECo
NOTE_26 | G28-43 has been rejected. Mail sozzetti 2012-09-22 | RCl
NOTE_27 | Dopo una discussione con Silvano e Raffaele, si conviene che lo stato evolutivo di MP16 (G9-47) e' troppo avanzato perche' le variazioni RV di breve periodo osservate siano estrinseche. (Mail Sozzetti 2013-02-26) | Aso
NOTE_28 | Mail Aso: 2013-04-28. M67 va con ogni probabilita' stoppata, esibisce una variazione di 2.5 km/s in cinque giorni, e' quasi sicuramente una binaria. | Aso
NOTE_29 | Mail Gmi 2013-04-23: la stella M57 va tolta dal campione in quanto una binaria come hanno mostrato le ultime osservazioni . | Gmi
NOTE_30 | Mail ASo 2013-05-25: M83 andrebbe stoppata. Come da allegato, chiaramente binaria, probabilmente di relativamente corto periodo a vedere l'andamento, e con una massa minima non grande (nana bruna), a giudicare dall'escursione in RV. Pero' qui siamo abbastanza sicuramente al di fuori del range di masse 'planetario'. Mail del 2013-06-02: Abbiamo eliminato anche la 72 | Aso+Gmi
NOTE_31 | MAIL di Laura Affer del 2013-07-26: Confermo l'eliminazione dal catalogo di M58 e M94 in quanto classificate come G/K da Lepine (mai osservate), M50 in quanto binaria, M45 early e gigante. Mail di Alessandro Sozzetti 2013-0725: Tra gli oggetti che ti hanno fornito Laura e Giusi, M50 ha un excursus di oltre 40 km/s tra le due osservazioni prese a distanza di un mese e mezzo. Va stoppata, piuttosto che messa a priorita' media. | Laf+Aso
NOTE_32 | Vedi Mail di S. desidera del 2013-07-26 | SDe
NOTE_33 | Vedi Mail di S. desidera del 2013-07-26 | SDe
NOTE_34 | Mail Laf 2013-07-29: sono tutte stelle rigettate: ID RA DEC Mv N. Obs Note M5 02 56 34.4 +55 26 33 10,48 1 Mis-Id in a multiple system M19 22 10 44.7 +07 54 33 10,92 1 Sub-arcsec Binary M26 02 01 49.0 +16 28 03 10,65 2 Sub-arcsec Binary | Laf
NOTE_35 | M STARS refused see E-Mail by Gmi and Laf of 2013-08-29: --- Qui invece c'e' la lista delle stelle definitivamente rigettate: 02 34 09.9 +68 43 21 9,9 M3 Fast Rotator 23 31 19.7 +59 44 52 9,9 M4 Early 02 56 34.4 +55 26 33 10,48 M5 Mis-Id in a multiple system 00 11 21.9 +58 37 03 11,21 M13 Early 22 10 44.7 +07 54 33 10,92 M19 Sub-arcsec Binary 02 01 49.0 +16 28 03 10,65 M26 Sub-arcsec Binary 03:16:13.8 +58:10:03 10.53 M32 Double or multiple system 03:27:53.2 +51:19:55 10.89 M35 Early 04:41:29.7 +13:13:16 11.26 M38 Binary 03:38:48.2 +54:59:21 11.27 M39 Early 04:58:30.4 +51:48:17 11.52 M42 Early 20:31:32.8 +55:57:48 10.12 M45 Early -- gigante 22:12:56.7 +55:04:50 11.02 M50 Binary 06:40:56.7 +63:53:25 11.27 M57 Binary 21:48:46.5 +40:19:43 11.27 M58 Early 11:15:12.0 +54:09:27 11.70 M66 Binary 05:46:48.7 +66:30:12 11.77 M67 Binary 20:43:34.5 +24:07:41 11.95 M72 Fast Rotator 13:19:33.3 +35:06:43 9.51 M83 Binary 14:25:46.7 +23:37:14 9.99 M94 Early | GMi+LAf
NOTE_36 | KP76 is the south component of a binary. The North component is KP22 | SDe
NOTE_37 | MAIL Aso 2013 -10- 07. Se Giusi non lo ha ancora comunicato, suggerisco senz'altro di stoppare M51. Se ci sono due spettri non c'e' modo di beccare le RV giuste. | Aso
NOTE_38 | Mail di Gmi del 2013-11-14: M49 è una binaria | Gmi
NOTE_39 | Mail Sde (2013-12-17) Target in stand By for all the LP | SDe
NOTE_40 | Wide companion of KP29=HAT-P-1=ADS 16402 B. Observed by mistake two times. Entry in KP catalog included to have the proper barycentric correction for the two RVs. Not to be observed in the future unless specifically required.See KP29 finding chart for the identification of the correct component to be observed. | Sde
NOTE_41 | MP10 La stella appare chiaramente doppia nell'autoguider. La debole compagna non e' indicata nella finding chart. Essendo a 2 arcsec, chiedere all'operatore di inserire una maschera per schermarla. | EPo
NOTE_42 | M93. Fa parte di un terzetto di stelle di uguale luminosita'. Il target e' la stella piu' a ovest. Usare la finding chart in caso di dubbio, ad esempio se il pointing non e' accurato e le tre stelle sono tutte nel campo dell'autoguida. | EPo
NOTE_43 | M33. Nel campo dell'autoguida compaiono due stelle. Il target e' la stella piu' a ovest. Usare la finding chart in caso di dubbio. | EPo
NOTE_44 | M84. Il nostro target e' 43 arcsec piu' a ovest di un target GTO, con cui forma una doppia visuale con moti propri comuni. Il target GAPS e' 2 mag piu' debole del target GTO. Puo' succedere che puntando il nostro target si verifichi un allarme di violata protezione. Puntare l'oggetto piu' debole e avvisare l'operatore di tranquillizzare il team GTO. Il tutto e' gia' successo nel febbraio 2014. | EPo

## APPENDIX C
RML1
RML2
RML3
RML4
RML5
RML6
RML7 | NOTE_25
RML8
RML9
RML9
RML10
RML11
RML12
RML13
RML14
RML14
RML15
RML15
RML16
RML16
RML17
RML17
RML17
RML18
RML19 | NOTE_10
M1
M2
M3 | NOTE_16
M4 | NOTE_35
M5 | NOTE_34
M6
M7
M8
M9
M10
M11
M12
M13 | NOTE_35
M14
M15
M16
M17
M18
M19 | NOTE_34
M20
M21
M22
M23
M24
M25
M26 | NOTE_34
M27
M28
M29
M30
M31
M32 | NOTE_17
M33 | NOTE_18
M34
M35
M36
M37
M38 | NOTE_35
M39 | NOTE_35
M40
M41
M42
M43 | NOTE_19
M44 | NOTE_20
M45 | NOTE_31
M46
M47
M48
M49 | NOTA_38
M50 | NOTE_31
M51 | NOTE_37
M52
M53
M54 | NOTE_21
M55
M56
M57 | NOTE_29
M58 | NOTE_31
M59
M60
M61 | NOTE_22
M62
M63
M64 | NOTE_23
M65
M66 | NOTE_35
M67 | NOTE_28
M68
M69 | NOTE_24
M70
M71
M72 | NOTE_30
M73
M74
M75
M76
M77
M78
M79
M80
M81
M82
M83 | NOTE_30
M84
M85
M86
M87
M88
M89
M90
M91
M92
M93
M94 | NOTE_31
M95
M96
M97
M98
M99
M100
M101
M102
M103
M104
M105
M106
KP1 | NOTE_03
KP2 | NOTE_04
KP3 | NOTE_05
KP4 | NOTE_06
KP5 | NOTE_07
KP6 | NOTE_08; NOTE_14; NOTE_38
KP7 | NOTE_09
KP8 | NOTE_10
KP9 | NOTE_10
KP10 | NOTE_10
KP11 | NOTE_10
KP12 | NOTE_10
KP13 | NOTE_10
KP14 | NOTE_10
KP15 | NOTE_10
KP16 | NOTE_10
KP17 | NOTE_10
KP18 | NOTE_10
KP19 | NOTE_10
KP20 | NOTE_10
KP21 | NOTE_10; NOTE_11
KP22 | NOTE_10; NOTE_12; NOTE_36
KP23 | NOTE_10
KP24 | NOTE_10
KP25 | NOTE_10
KP26 | NOTE_10
KP27 | NOTE_10
KP28 | NOTE_10
KP29 | NOTE_10; NOTE_13
KP30 | NOTE_10
KP31 | NOTE_10
KP32
KP33
KP34
KP35
KP36
KP37
KP38
KP39
KP40
KP41
KP42
KP43
KP44
KP45
KP46
KP47
KP48
KP49
KP50
KP51 | NOTE_32
KP52 | NOTE_39
KP53 | NOTE_39
KP54
KP55
KP56
KP57
KP58 | NOTE_39
KP59
KP60
KP61
KP62 | NOTE_39
KP63
KP64
KP65
KP66
KP67
KP68
KP69
KP70
KP71
KP72 | NOTE_15
KP73
KP74
KP75 | NOTE_32
KP76 | NOTE_36; NOTE_12
KP77 | NOTE_40
KP78
KP79
MP1
MP2
MP3
MP4
MP5
MP6
MP7
MP8
MP9
MP10 | NOTE_41
MP11
MP12
MP13
MP14
MP15
MP16 | NOTE_27
MP17
MP18 | NOTE_26
MP19
MP20
MP21
MP22
MP23
MP24
MP25
MP26
MP27
MP28
MP29
MP30
MP31
MP32
MP33
MP34
MP35
MP36
MP37
MP38
MP39
MP40
MP41
MP42
MP43
MP44
MP45
MP46
MP47
MP48
MP49
MP50
MP51
MP52
MP53
MP54
MP55
MP56
MP57
MP58
MP59
MP60
MP61
OC001
OC002
OC003
OC004
OC005
OC006
OC007
OC008
OC009
OC010
OC011
OC012
OC013
OC014
OC015
OC016
OC017
OC018
OC019
OC020
OC021
OC022
OC023
OC024
OC025
OC026
OC027
OC028
OC029
OC030
OC031
OC032
OC033
OC034
OC035
OC036
OC037
OC038
OC039
OC040
OC041
OC042
OC043
OC044
OC045
OC046
OC047
OC048
OC101
OC102
OC103
OC104
OC105
OC106
OC107
OC108
OC109
OC110
OC111
OC112
OC113
OC114
OC115
OC116
OC117
OC118
OC119
OC120
OC121
OC122
OC123
OC124
OC125
OC126
OC127
OC128
OC129
OC130
OC131
OC132
OC133
OC134
OC135
OC136
IP01 | NOTE_02
AST01 | NOTE_01
Note on A28: Riccardo Claudi: SEE NOTE_16
Note on A57: Riccardo Claudi: SEE NOTE_17
Note on A228: Riccardo Claudi: SEE NOTE_26
Note on A275: Office 2004 Test Drive User: This object has been rejected. See 2012-12-21 E-Mail by LMa
Note on A277: Office 2004 Test Drive User: This object has been rejected. See 2012-12-21 E-Mail by LMa
Note on A287: Office 2004 Test Drive User: This object has been rejected. See 2012-12-21 E-Mail by LMa

## APPENDIX D
# | name | ut_ingress | ut_egress